## Sheet1
Date of Planning Board Approval: January 22, 2008
Site Plan and Subdivision. + waiver of housing replacement granted
130 Eastern Promenade - The Estates at Longfellow Inn
Met | Date | Condition | Notes
1.31.08 |  | That the revised boundary survey submitted by the applicant be reviewed and approved by Public Works prior to the issuance of a building permit. | dan reviewed and approved this.
done. |  | All final plan sheets must stamped and signed by a professional engineer.
|  | All comments submitted by Public Works in their memorandum dated January 16, 2008 must be addressed and approved by Public Works prior to the issuance of a building permit. | Forwarded these comments to Susanne (1/26/08) - I have the dtail sheet Dan referred to. Asked Susanne for electornic copy to forward to him on 1/25/08.
yes | 2008-02-08 | All comments submitted by Jeff Tarling, City Arborist pertaining to the submitted landscaping plan and identified in his review letter dated January 18, 2008 must be addressed and approved by him prior to the issuance of a building permit. | forwarded these comments again to applicant by email. (1/25/08)
yes | 2008-02-08 | The proposed street tree along the Eastern Promenade should be revised to show an Autumn Blaze Maple (Acer freemanii). This change to the plans must be reviewed and approved by Jeff Tarling, City Arborist prior to the issuance of a building permit.
yes | 1.18.08 | That the trash enclosure, as identified on the plans, be completely enclosed, including the top. The proposed enclosure must be reviewed and approved by the Planning Authority prior to the issuance of a building permit. | applicant submitted revised detail drawing showing trash enclosure with 4 sides and top
yes | 1.31.08 | Evidence must be submitted to the Planning Authority that the proposal meets the required open space ratio as defined in the City Code. This evidence must be reviewed and approved by the City Zoning Administrator prior to recording of the recording plat. | Marge reviewed and approved. See Marge's 1.31.08 memo - ui
yes | 1.25.08 | An updated deed for the property showing the current owner as Casco Bay Ventures (the applicant) must be reviewed and approved by the Planning Authority prior to recording of the recording plat. | reviewed and signed off by penny.