# SECTION 01027 - APPLICATIONS FOR PAYMENT

# PART 1 - GENERAL

# 1.1	RELATED DOCUMENTS

- Site drawings produced by Pinkham and Greer Consulting Engineers, foundation/basement plan drawings produced by TFH Architects PA and Structural Design Consulting, building drawings produced by TFH Architects, mechanical drawings produced by TFH Architects, electrical and lighting drawings produced by TFH Architects.  Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections apply to all sections.

# 1.2	SUMMARY

A.	This Section specifies administrative and procedural requirements governing the Contractor's Applications for Payment.

# 1.3	SCHEDULE OF VALUES

A.	Coordination:  Coordinate preparation of the Schedule of Values with preparation of the Contractor's Construction Schedule.

B.	Coordination:  Each subcontractor shall coordinate preparation of its Schedule of Values for its part of the Work with preparation of the Contractors' Construction Schedule.

1.	Correlate line items in the Schedule of Values with other required administrative schedules and forms, including:

a.	Contractor's Construction Schedule.

b.	Application for Payment forms.

c.	List of subcontractors.

2.	Submit the Schedule of Values to the Architect at the earliest possible date but no later than 7 days before the date scheduled for submittal of the initial Applications for Payment.

C.	Format and Content:  Use the Project Manual table of contents as a guide to establish the format for the Schedule of Values.  Provide at least one line item for each Specification Section.

1.	Identification:  Include the following Project identification on the Schedule of Values:

a.	Project name and location.

b.	Name of the Architect.

c.	Project number.

d.	Contractor's name and address.

e.	Date of submittal.

2.	Arrange the Schedule of Values in tabular form with separate columns to indicate the following for each item listed:

a.	Related Specification Section or Division.

b.	Description of Work.

c.	Name of subcontractor.

d.	Name of manufacturer or fabricator.

e.	Name of supplier.

f.	Change Orders (numbers) that affect value.

g.	Dollar value.

1.	Percentage of Contract Sum to nearest one-hundredth percent, adjusted to total 100 percent.

- Provide a breakdown of the Contract Sum in sufficient detail to facilitate continued evaluation of Applications for Payment and progress reports.  Coordinate with the Project Manual table of contents.  Break principal subcontract amounts down into several line items.

4.	Round amounts to nearest whole dollar; the total shall equal the Contract Sum.

5.	Schedule Updating:  Update and resubmit the Schedule of Values prior to the next Applications for Payment when Change Orders or Construction Change Directives result in a change in the Contract Sum.

# 1.4	APPLICATIONS FOR PAYMENT

A.	Each Application for Payment shall be consistent with previous applications and payments as certified by the Architect and paid for by the Owner.

1.	The initial Application for Payment, the Application for Payment at time of Substantial Completion, and the final Application for Payment involve additional requirements.

B.	Payment-Application Times:  The date for each progress payment is the 15th day of each month.  The period covered by each Application for Payment starts on the day following the end of the preceding period and ends 15 days prior to the date for each progress payment.

C.	Payment-Application Forms:  Use AIA Document G702 and Continuation Sheets G703 as the form for Applications for Payment.

D.	Application Preparation:  Complete every entry on the form.  Include notarization and execution by a person authorized to sign legal documents on behalf of the Contractor.  The Architect will return incomplete applications without action.

1.	Entries shall match data on the Schedule of Values and the Contractor's Construction Schedule.  Use updated schedules if revisions were made.

2.	Include amounts of Change Orders and Construction Change Directives issued prior to the last day of the construction period covered by the application.

E.	Transmittal:  Submit 3 signed and notarized original copies of each Application for Payment to the Architect by a method ensuring receipt within 24 hours.  One copy shall be complete, including waivers of lien and similar attachments, when required.

1.	Transmit each copy with a transmittal form listing attachments and recording appropriate information related to the application, in a manner acceptable to the Architect.

F.	Waivers of Mechanics Lien:  With each Application for Payment, submit waivers of mechanics liens from subcontractors, sub-subcontractors and suppliers for the construction period covered by the previous application.

1.	Submit partial waivers on each item for the amount requested, prior to deduction for retainage, on each item.

2.	When an application shows completion of an item, submit final or full waivers.

3.	The Owner reserves the right to designate which entities involved in the Work must submit waivers.

G.	Initial Application for Payment:  Administrative actions and submittals, that must precede or coincide with submittal of the first Application for Payment, include the following:

1.	List of subcontractors.

2.	Schedule of Values.

3.	Contractor's Construction Schedule (preliminary if not final).

4.	Submittal Schedule (preliminary if not final).

5.	List of Contractor's staff assignments.

6.	Copies of building permits.

7.	Copies of authorizations and licenses from governing authorities for performance of the Work.

8.	Initial progress report.

9.	Report of pre-construction meeting.

10.	Certificates of insurance and insurance policies.

11.	Performance and payment bonds.

12.	Data needed to acquire the Owner's insurance.

13.	Initial settlement survey and damage report, if required.

H.	Application for Payment at Substantial Completion:  Following issuance of the Certificate of Substantial Completion, submit an Application for Payment.

1.	This application shall reflect Certificates of Partial Substantial Completion issued previously for Owner occupancy of designated portions of the Work.

2.	Administrative actions and submittals that shall precede or coincide with this application include:

a.	Occupancy permits and similar approvals.

b.	Warranties (guarantees) and maintenance agreements.

c.	Maintenance instructions.

d.	Changeover information related to Owner's occupancy, use, operation, and maintenance.

e.	Final cleaning.

f.	Application for reduction of retainage and consent of surety.

g.	Advice on shifting insurance coverages.

h.	List of incomplete Work, recognized as exceptions to Architect's Certificate of Substantial Completion.

i.	Ten percent retainage on all progress payments will be required until the project is at least 50% complete.  At 50% completion the contractor may request, in writing to the owner and MSHA, to reduce the retainage on any future progress payments to 0% while maintaining the existing balance until the time of substantial completion.

I.	Final Payment Application:  Administrative actions and submittals that must precede or coincide with submittal of the final Application for Payment include the following:

1.	Completion of Project closeout requirements.

2.	Completion of items specified for completion after Substantial Completion.

3.	Ensure that unsettled claims will be settled.

4.	Ensure that incomplete Work is not accepted and will be completed without undue delay.

5.	Transmittal of required Project construction records to the Owner.

6.	Certified property survey.

7.	Proof that taxes, fees, and similar obligations were paid.

8.	Removal of temporary facilities and services.

9.	Removal of surplus materials, rubbish, and similar elements.

# PART 2 - PRODUCTS  (Not Applicable)

# PART 3 - EXECUTION  (Not Applicable)

# END OF SECTION 01270