# SECTION 01200 – PROJECT MEETINGS

# PART I – GENERAL

  - RELATED DOCUMENTS

- Site drawings produced by Pinkham and Greer Consulting Engineers, foundation/basement plan drawings produced by TFH Architects PA and Structural Design Consulting, building drawings produced by TFH Architects, mechanical drawings produced by TFH Architects, electrical and lighting drawings produced by TFH Architects.  Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections apply to all sections.

  - SUMMARY

- This Section specifies administrative and procedural requirements necessary for project meetings including, but not necessarily limited to, the following:

  - Pre-construction conferences.

  - Pre-installation conferences.

  - Progress meetings.

- Related Sections:  The following Sections contain requirements that relate to this Section:

  - Division 1 Section “Coordination” for procedures for coordinating project meetings with other construction activities.

  - Division 1 Section “Submittals” for submitting the Contractor’s Construction Schedule.

  - PRE-CONSTRUCTION CONFERENCE

- Schedule a pre-construction conference before starting construction of each triplex, at a time convenient to the Owner and the Architect.  Hold the conference at the Project Site or another convenient location.  Conduct the meeting to review responsibilities and personnel assignments.

- Attendees:  Authorized representatives of the Owner, Architect and their consultants, representatives of the Maine State Housing Authority; the Contractor and its superintendent; major subcontractors; manufacturers; supplies and other concerned parties shall attend the conference.  All participants at the conference shall be familiar with the Project and authorized to conclude matters relating to the Work.  The Owner and/or the Architect will be responsible for leading the meeting.

- Agenda:  Discuss items of significance that could affect progress, including the following:

  - Tentative construction schedule.

  - Critical work sequencing.

  - Designation of responsible personnel.

  - Procedures for processing field decisions and Change Orders.

  - Procedures for processing Applications for Payment.

  - Distribution of Contract Documents.

  - Submittal of Shop Drawings, Product Data and Samples.  (Contractor to provide a list of submissions along with approximate submission dates).

  - Preparation of record documents.

  - Use of the premises.

  - Parking availability.

  - Office, work and storage areas.

  - Equipment deliveries and priorities.

  - Safety procedures.

  - First aid.

  - Security.

  - Housekeeping.

  - Working hours.

  - PRE-INSTALLATION CONFERENCES

- Conduct a pre-installation conference at the Project Site before each construction activity that requires coordination with other construction.

- Attendees:  The Installer and representatives of manufacturers and fabricators involved in or affected by the installation, and its coordination or integration with other materials and installations that have preceded or will follow, shall attend the meeting.  Advise the Architect of scheduled meeting dates.

  - Review the progress of other construction activities and preparations for the particular activity under consideration at each pre-installation conference, including requirements for the following:

    - Contract Documents.

    - Options.

    - Related Change Orders.

    - Purchases.

    - Deliveries.

    - Shop Drawings, Product Data and quality-control samples.

    - Review of mockups.

    - Possible conflicts.

    - Compatibility problems.

    - Time schedules.

    - Weather limitations.

    - Manufacturer’s recommendations.

    - Warranty requirements.

    - Compatibility of materials.

    - Acceptability of substrates.

    - Temporary facilities.

    - Space and access limitations.

    - Governing regulations.

    - Safety.

    - Inspecting and testing requirements.

    - Required performance results.

    - Recording requirements.

    - Protection.

    - Procedures for working on abutting properties.

  - Record significant discussions and agreements and disagreements of each conference, and the approved schedule.  Promptly distribute the record of the meeting to everyone concerned, including the Owner and the Architect.

  - Do not proceed with the installation if the conference cannot be successfully concluded.  Initiate whatever actions are necessary to resolve impediments to performance of Work and reconvene the conference at the earliest feasible date.

  - PROGESS MEETINGS

- Conduct progress meetings at the Project Site or other designated site at regular intervals, but not less than every two weeks.  Notify the Owner and the Architect of scheduled meeting dates.  Coordinate dates of meetings with preparation of the payment request.

- Attendees:  In addition to representatives of the Owner and the Architect, Maine State Housing Authority, each subcontractor, supplier or other entity concerned with current progress or involved in planning, coordination or performance of future activities shall be represented at these meetings.  All participants at the conference shall be familiar with the Project and authorized to conclude matters relating to the Work.

- Agenda:  Review and correct or approve minutes of the previous progress meeting.  Review other items of significance that could affect progress.  Include topics for discussion as appropriate to the status of the Project.

  - Contractor’s Construction Schedule:  Review progress since the last meeting.  Determine where each activity is in relation to the Contractor’s Construction Schedule, whether on time or ahead or behind schedule.  Determine how construction behind schedule will be expedited; secure commitments from parties involved to do so.  Discuss whether schedule revisions are required to insure that current and subsequent activities will be completed within the Contract Time.

  - Review the present and future needs of each entity present, including the following:

    - Interface requirements.

    - Time.

    - Sequences.

    - Status of submittals.

    - Deliveries.

    - Off-site fabrication problems.

    - Access.

    - Site utilization.

    - Temporary facilities and services.

    - Hours of work.

    - Hazards and risks.

    - Housekeeping.

    - Quality and work standards.

    - Change Orders.

    - Documentation of information for payment requests.

- Reporting:  No later than 3 days after each meeting, distribute minutes of the meeting to each party present and to parties who should have been present.  Include a brief summary, in narrative form, of progress since the previous meeting and report.

  - Schedule Updating:  Revise the Contractor’s Construction Schedule after each progress meeting where revisions to the schedule have been made or recognized.  Issue the revised schedule concurrently with the report of each meeting.

# PART 2 – PRODUCTS (not applicable)

# PART 3 – EXECUTION (not applicable)

# END OF SECTION 01200