# SECTION 01311 - SCHEDULES AND REPORTS

# PART 1 - GENERAL

# 1.1	RELATED DOCUMENTS

A.	Site drawings produced by Coffin Engineering, building construction drawings produced by TFH Architects PA with Structural Design Consulting.  Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

# 1.2	SUMMARY

A.	This Section includes administrative and procedural requirements for schedules and reports required for proper performance of the Work, including:

1.	Contractor's construction schedule.

2.	Submittal schedule.

3.	Daily construction reports.

4.	Field correction reports.

5.	Special reports.

B.	Related Sections:  The following Sections contain requirements that relate to this Section:

1.	Division 1 Section "Applications for Payment" specifies requirements for submittal of the Schedule of Values.

2.	Division 1 Section "Project Meetings" specifies requirements for submittal and distribution of meeting and conference minutes.

3.	Division 1 Section "Quality Control" specifies requirements for submittal of inspection and test reports.

4.	Division 1 Section "Materials and Equipment" specifies requirements for submittal of the list of products.

# 1.3	SUBMITTAL PROCEDURES

A.	Coordination:  Coordinate preparation and processing of schedules and reports with performance of other construction activities.

# 1.4	CONTRACTOR'S CONSTRUCTION SCHEDULE

A.	Bar-Chart Schedule:  Prepare a comprehensive, fully developed, horizontal bar-chart-type, contractor's construction schedule.  Base the schedule on the Preliminary Construction Schedule and whatever updating and feedback was received since the start of the Project.

B.	Cost Correlation:  At the head of the schedule, provide a cost correlation line, indicating planned and actual costs.  On the line, show dollar volume of Work performed as of the dates used for preparation of payment requests.

1.	Refer to Division 1 Section "Applications for Payment" for cost reporting and payment procedures.

C.	Distribution:  Following response to the initial submittal, print and distribute copies to the Architect, Owner, subcontractors, and other parties required to comply with scheduled dates.  Post copies in the Project meeting room and temporary field office.

1.	When revisions are made, distribute to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in construction activities.

D.	Schedule Updating:  Revise the schedule after each meeting, event, or activity where revisions have been recognized or made.  Issue the updated schedule concurrently with the report of each meeting.

# 1.5	SUBMITTAL SCHEDULE

A.	After development and acceptance of the Contractor's Construction Schedule, prepare a complete schedule of submittals.  Submit the schedule within 10 days of the date required for submittal of the Contractor's Construction Schedule.

1.	Coordinate Submittal Schedule with the list of subcontracts, Schedule of Values and the list of products as well as the Contractor's Construction Schedule.

B.	Prepare the schedule in chronological order.  Provide the following information:

1.	Scheduled date for the first submittal.

2.	Related Section number.

3.	Submittal category.

4.	Name of the subcontractor.

5.	Description of the part of the Work covered.

6.	Scheduled date for resubmittal.

7.	Scheduled date for the Architect's final release or approval.

C.	Distribution:  Following the Architect's response to the initial submittal, print and distribute copies to the Architect, Owner, subcontractors, and other parties required to comply with submittal dates indicated.

1.	Post copies in the Project meeting room and temporary field office.

2.	When revisions are made, distribute to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned part of the Work and are no longer involved in construction activities.

D.	Schedule Updating:  Revise the schedule after each meeting or other activity where revisions have been recognized or made.  Issue the updated schedule concurrently with the report of each meeting.

# 1.6	REPORTS

A.	Daily Construction Reports:  Prepare a daily construction report recording the following information concerning events at the site.  Submit duplicate copies to the Architect at weekly intervals:

1.	List of subcontractors at the site.

2.	List of separate contractors at the site.

3.	Approximate count of personnel at the site.

4.	High and low temperatures, general weather conditions.

5.	Accidents.

6.	Meetings and significant decisions.

7.	Unusual events (refer to special reports).

8.	Stoppages, delays, shortages, and losses.

9.	Meter readings and similar recordings.

10.	Emergency procedures.

11.	Orders and requests of governing authorities.

12.	Change Orders received, implemented.

13.	Services connected, disconnected.

14.	Equipment or system tests and startups.

15.	Partial Completions, occupancies.

16.	Substantial Completions authorized.

B.	Field Correction Reports:  When the need to take corrective action that requires a departure from the Contract Documents arises, prepare a detailed report.  Include a statement describing the problem and recommended changes.  Indicate reasons the Contract Documents cannot be followed.  Submit a copy to the Architect immediately.

# 1.7	SPECIAL REPORTS

A.	General:  Submit special reports directly to the Owner within one day of an occurrence.  Submit a copy to the Architect and other parties affected by the occurrence.

B.	Reporting Unusual Events:  When an event of an unusual and significant nature occurs at the site, prepare and submit a special report.  List the chain of events, persons participating, response by the Contractor's personnel, an evaluation of the results or effects and similar pertinent information.  Advise the Owner in advance when such events are known or predictable.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION (Not Applicable)

# END OF SECTION 01311