SECTION 01300

SUBMITTALS, MEETINGS AND RECORD DOCUMENTS

1. 	GENERAL

1.1	CONSTRUCTION SCHEDULE

A.  	Schedule shall show activities, itemized according to specification Section, and be organized in 		CPM form and show both projected and actual progress of work.

B.  	Arrange schedule to indicate required sequencing of units, and to show time allowances for 			submittals, inspections, and similar time margins.

C.  	Show critical submittal dates related to each time bar, or prepare a separate coordinated listing 		of critical submittal dates.

D.  	Submit updated schedule monthly, together with application for payment.

1.2 	SCHEDULE OF VALUES

A.  	Refer to General Conditions, Paragraph 9.2 for general provisions concerning schedule of 			values.

B.  	For these submittals, use AIA Document G702/703, Application and Certificate for Payment.

C.  	Use specifications Sections as listed in Table of Contents as basis for format for listing costs.

D.  	Itemize separately general cost items, such as bonds and allowances.

E.  	Itemize change orders separately as they are approved.

1.3	APPLICATION FOR PAYMENT

A.  	Refer to General Conditions, Paragraph 9.3, for general provisions concerning applications for 		payment.

B.  	Use AIA Form G702/703, fully completed and executed.

C. 	Submit the forms in triplicate including attachment of waivers and similar documentation with 		one copy.

1.4 	SHOP DRAWINGS, PROJECT DATA, SAMPLES

A.  	Refer to General Conditions, Product Data and Samples, paragraph 3.12, for general provisions 		covering this type of submittal.

B.  	Coordinate the preparation and processing of work-related submittals with the performance of 		the work.  Coordinate each separate submittal with other submittals and related activities that 			require sequential activity.  Coordinate the submittal of different units of interrelated work so 			that one submittal will not be delayed by the necessity of reviewing a related submittal.

C.  	Architect/Engineer Review:

1.  	Allow ten working days for the Architect/Engineer's initial processing of each submittal.  			Allow one week for reprocessing each submittal.  No extension of time will be authorized 			because of failure to transmit submittals to the Architect/Engineer sufficiently in advance 			of the work.

2.  	The Architect/Engineer will stamp each submittal to be returned with a uniform, self-				explanatory action stamp, appropriately marked and executed to indicate the status of the 			submittal.

D.  	Mark each submittal with a permanent label for identification.  Provide project name, date, 			name of Architect/Engineer, name of Contractor, number and title of appropriate specification 		section and similar definitive information.  Provide a space on the label for Contractors and 			Architect/Engineer's review markings.

E.  	Package each submittal appropriately for transmittal and handling.  Send each submittal from 			the Contractor to the Architect/Engineer and other destinations using AIA Transmittal Form 			G810.

F.  	Provide additional copies of submittals required by governing authorities that are in addition to 		copies specified for submittal to the Architect/Engineer.

G.  	Where it is necessary to provide intermediate submittals between the initial and final 				submittals, provide and process intermediate submittals in the same manner as for initial 				submittals.

H. 	Submit as follows:

1.  	Shop drawings (original drawings prepared by Contractor or sub-contractor illustrating 				fabrication, layout, erection details, etc.): six prints, or one reproducible transparency and 			one opaque print, to Architect.

2.  	Manufacturers' specifications, installation instructions, charts, schedules, catalogs, 					brochures, etc.:  number of copies required by Contractor for distribution, plus one copy 				for Architect's retention.

3. 	Samples:  one sample to Architect only, unless otherwise specified.

4.  	In submitting shop drawings and product data to Architect, use separate transmittals for 				material in different specification Sections, with applicable specification Section clearly 				numbered.

I.  	Architect will review submittals within ten working days, measured from date of receipt by 			Architect until date of mailing.  Contractor shall promptly make corrections and resubmit when 		so directed.  Where submittal is marked "Approved as Noted" or similar, assume that all items 		are approved other than those to which specific exception is taken.  Do not delay fabrication, 			assembly and delivery pending receipt of entirely "Approved" submittal.

J. 	Distribute approved submittals to job site and record document files, and to suppliers and sub-		contractors as required.  Samples not designated by Contractor for incorporation into Work 			shall be kept on file until job completion.  Any sample not reclaimed within 30 days after job 			completion will be considered unclaimed, and will be disposed of as directed by Architect.

1.5 	PROJECT RECORD DOCUMENTS

A.  	Keep on file at job site one complete set of up-to-date Contract Documents, including drawings 		and specifications, addenda, shop drawings and product data, testing data, change orders, field 		orders, and other modifications.  Documents shall be neatly and securely stored in files or on 			racks, clearly indexed by trade activity or specification Section, and shall not be used for 				construction purposes.

B.  	Legibly mark significant field changes such as following, using colored pencils or felt-tipped 			pens:

1.  	Drawings:  locations of concealed utilities, field changes of dimension and detail, changes 			resulting from change order or field order, and details not on original drawings.

2.  	Specifications:  manufacturer and model number of equipment actually installed.

3.  	Shop drawings and manufacturers' literature:  changes made after Architect's review.

C.  	At completion of Work, deliver completed record documents to Architect.  Final payment for 			Project will not be made until Architect reviews and approves these documents.

1.6	 SUBSTANTIAL COMPLETION

A.  	Refer to General Conditions, Article 9, Substantial Completion, for general provision 				concerning substantial Completion.

B.  	Following issuance by Architect/Engineer of Certificate of Substantial Completion, Contractor 		may submit special payment request, provided the following have been completed:

1.  	Obtain permits, certificates of inspection and other approval and releases by governing 				authorities, required for Owner's occupancy and use of project.

2.  	Submit warranties and similar documentation.

3.  	Submit maintenance manuals and provide instruction of Owner's operational/maintenance 			personnel.

4.  	Complete final cleaning of the work.

5.  	Submit record documents.

6.  	Submit listing of work to be completed before final acceptance.

C.  	Following completion of the following requirements, final payment request may be submitted:

1.  	Complete work listed as incomplete at time of substantial completion, or otherwise assure 			Owner of subsequent completion of individual incomplete items.

2. 	 Settle liens and other claims, or assure Owner of subsequent settlement.

3. 	 Submit proof of payment on fees, taxes and similar obligations.

4.  	Transfer operational, access, security and similar provisions to Owner; and remove 					temporary facilities, tools and similar items.

5.  	Completion of requirements specified in "Project Closeout" section.

6. 	Obtain consent of surety for final payment.

END OF SECTION