# SECTION 01300

# SUBMITTALS

# PART 1 - GENERAL

# 1.01	RELATED DOCUMENTS

- Drawings and general provisions of Contract, including General and Special Provisions and other Division-1 Specification Sections, apply to this Section.

# 1.02	SUMMARY

- This Section specifies administrative and procedural requirements for submittals required for performance of the Work, including:

  - Work progress schedule, herewith referred to as the contractor's construction schedule.

  - Submittal schedule.

  - Shop Drawings.

  - Product Data.

  - Samples.

- Administrative Submittals:  Refer to other Division-1 Sections and other Contract Documents for requirements for administrative submittals.  Such submittals include, but are not limited to:

  - Permits.

  - Applications for payment.

  - Performance and payment bonds.

  - Insurance certificates.

  - List of Subcontractors.

- The Schedule of Values submittal is included in Section "Applications for Payment."

- Inspection and test reports are included in Section "Quality Control Services."

# 1.03	SUBMITTAL PROCEDURES

- Coordination:  Coordinate preparation and processing of submittals with performance of construction activities.  Transmit each submittal sufficiently in advance of performance of related construction activities to avoid delay.

  - Coordinate each submittal with fabrication, purchasing, testing, delivery, other submittals and related activities that require sequential activity.

  - Coordinate transmittal of different types of submittals for related elements of the Work so processing will not be delayed by the need to review submittals concurrently for coordination.

    - The Architect reserves the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.

    - The Owner reserves the right to approve all submittals.

- Processing:  Allow sufficient review time so that installation will not be delayed as a result of the time required to process submittals, including time for resubmittals.

  - Allow two weeks for initial review.  Allow additional time if processing must be delayed to permit coordination with subsequent submittals.  The Architect will promptly advise the Contractor when a submittal being processed must be delayed for coordination.

  - If an intermediate submittal is necessary, process the same as the initial submittal.

  - Allow two weeks for reprocessing each submittal.

  - No extension of Contract Time will be authorized because of failure to transmit submittals to the Architect sufficiently in advance of the Work to permit processing.

- Submittal Preparation:  Place a permanent label or title block on each submittal for identification.  Indicate the name of the entity that prepared each submittal on the label or title block.

  - Provide a space approximately 4" x 5" on the label or beside the title block on Shop Drawings to record the Contractor's review and approval markings and the action taken.

  - Include the following information on the label for processing and recording action taken.

    - Project name.

    - Date.

    - Name of Owner.

    - Name and address of Architect.

    - Name and address of Contractor.

    - Name and address of subcontractor.

    - Name and address of supplier.

    - Name of manufacturer.

    - Number and title of appropriate Specification Section.

    - Drawing number and detail references, as appropriate.

- Submittal Transmittal:  Package each submittal appropriately for transmittal and handling. Transmit each submittal from Contractor to Architect using a transmittal form.  Submittals received from sources other than the Contractor will be returned without action.

# 1.04	CONTRACTOR'S CONSTRUCTION SCHEDULE

- Bar-Chart Schedule:  Prepare a fully developed, horizontal bar-chart type Contractor's construction schedule.  Submit within 30 days of the date established for "Commencement of the Work".

  - Provide a separate time bar for each significant construction activity.  Provide a continuous vertical line to identify the first working day of each week.  Use the same breakdown of units of the Work as indicated in the "Schedule of Values".

  - Prepare the schedule on a sheet, or series of sheet, of stable transparency, or other reproducible media, of sufficient width to show data for the entire construction period.

  - Secure time commitments for performing critical elements of the Work from parties involved.

  - Coordinate each element on the schedule with other construction activities; include minor elements involved in the sequence of the Work.  Show each activity in proper sequence.  Indicate graphically sequences necessary for completion of related portions of the Work.

  - Coordinate the Contractor's construction schedule with the schedule of values, list of subcontracts, submittal schedule, progress reports, payment requests and other schedules.

  - Indicate completion in advance of the date established for Substantial Completion.  Indicate Substantial Completion on the schedule to allow time for the Architect's procedures necessary for certification of Substantial Completion.

- Phasing:  Provide notations on the schedule to show how the sequence of the Work is affected by requirements for phased completion to permit Work by separate Contractors and partial occupancy by the Owner prior to Substantial Completion.

- Work Stages:  Indicate important stages of construction for each major portion of the Work, including testing and installation.

- Site Demolition.

- Site Utilities.

- Framing Work.

- Sub-Trade Work.

- Equipment Installation.

- Cost Correlation:  At the head of the schedule, provide a two item cost correlation line, indicating "precalculated" and "actual" costs.  On the line show dollar-volume of Work performed as of the dates used for preparation of payment requests.

- Refer to Section "Applications for Payment" for cost reporting and payment procedures.

- Distribution:  Following response to the initial submittal, print and distribute copies to the Architect, Owner, subcontractors and other parties required to comply with scheduled dates.  Post copies in the Project meeting room and temporary field office.

- When revisions are made, distribute to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in construction activities.

- Schedule Updating:  Revise the schedule after each meeting or activity, where revisions have been recognized or made.  Issue the updated schedule concurrently with report of each meeting.

# 1.05	SUBMITTAL SCHEDULE

- After development and acceptance of the Contractor's construction schedule, prepare a complete schedule of submittals.  Submit the schedule within 10 days of the date required for establishment of the Contractor's construction schedule.

  - Coordinate submittal schedule with the list of subcontracts, schedule of values and the list of products as well as the Contractor's construction schedule.

  - Prepare the schedule in chronological order; include submittals required during the first 90 days of construction.

- Distribution:  Following response to initial submittal, print and distribute copies to the Architect, Owner, subcontractors, and other parties required to comply with submittal dates indicated.  Post copies in the Project meeting room and field office.

- When revisions are made, distribute to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portions of the Work and are no longer involved in construction activities.

  - Schedule Updating:  Revise the schedule after each meeting or activity, where revisions have been recognized or made.  Issue the updated schedule concurrently with report of each meeting.

1.06	DAILY CONSTRUCTION REPORTS

- Prepare a daily construction report, recording the following information concerning events at the site; and submit duplicate copies to the Architect at weekly intervals:

  - List of subcontractors at the site.

  - Accidents and unusual events.

  - Meetings and significant decisions.

  - Orders and requests of governing authorities.

  - Change Orders received, implemented.

  - Services connected, disconnected.

  - Equipment or system tests and start-ups.

  - Partial Completions.

# 1.07	SHOP DRAWINGS

- Submit newly prepared information, drawn to accurate scale.  Indicate deviations from the Contract Documents.  Do not reproduce Contract Documents or copy standard information as the basis of Shop Drawings.  Standard information prepared without specific reference to the Project is not considered Shop Drawings.

- Shop Drawings include fabrication and installation drawings, setting diagrams, schedules, patterns, templates and similar drawings.  Include the following information:

  - Dimensions.

  - Identification of products and materials included.

  - Compliance with specified standards.

  - Notation of coordination requirements.

  - Notation of dimensions established by field measurement.

- Sheet Size:  Except for templates, patterns and similar full-size Drawings, submit Shop Drawings on sheets at least 8 1/2" x 11" but no larger than 36" x 48".

- Submit four (4) blue- or black-line prints and two (2) additional prints where required for maintenance manuals.

One (1) print will be retained; the remainder returned.

  - One of the prints returned shall be maintained as a "Record Document".

  - Do not use Shop Drawings without an appropriate final stamp indicating action taken in connection with construction.

- Shop drawings for Division 15 and Division 16 shall be submitted in accordance with Section 15000/16000 (1.27).

# 1.08	PRODUCT DATA

- Collect Product Data into a single submittal for each element of construction or system.  Product Data includes printed information such as manufacturer's installation instructions, catalog cuts, standard color charts, roughing-in diagrams and templates, standard wiring diagrams and performance curves.  Where Product Data must be specially prepared because standard printed data is not suitable for use, submit as "Shop Drawings."

- Mark each copy to show applicable choices and options.  Where printed Product Data includes information on several products, some of which are not required, mark copies to indicate the applicable information.  Include the following information:

  - Manufacturer's printed recommendations.

  - Compliance with recognized trade association standards.

  - Compliance with recognized testing agency standards.

  - Application of testing agency labels and seals.

  - Notation of dimensions verified by field measurement.

  - Notation of coordination requirements.

Do not submit Product Data until compliance with requirements of the Contract Documents has been confirmed.

- Submittals:  Submit 6 copies of each required submittal; submit 6 copies where required for maintenance manuals.

The Architect and Owner will retain one, and will return the other marked with action taken and corrections or modifications required.

- Unless noncompliance with Contract Document provisions is observed, the submittal may serve as the final submittal.

- Distribution:  Furnish copies of final submittal to installers, Owner and others required for performance of construction activities.  Show distribution on transmittal forms.

- Do not proceed with installation until an applicable copy of Product Data applicable is in the installer's possession.

- Do not permit use of unmarked copies of Product Data in connection with construction.

# 1.09	SAMPLES

- Submit full-size, fully fabricated Samples cured and finished as specified and physically identical with the material or product proposed.  Samples include partial sections of manufactured or fabricated components, cuts or containers of materials, color range sets, and swatches showing color, texture and pattern.

Mount, display or package Samples in the manner specified to facilitate review of qualities indicated.  Include the following:

  - Generic description of the Sample.

  - Sample source.

  - Product name or name of manufacturer.

  - Compliance with recognized standards.

  - Availability and delivery time.

- Submit Samples for review of kind, color, pattern and texture, for a final check of these characteristics with other elements, and for a comparison of these characteristics between the final submittal and the actual component as delivered and installed.

- Where variation in color, pattern, texture or other characteristics are inherent in the material or product represented, submit multiple units (not less than 3), that show approximate limits of the variations.

- Submittals:  Submit 4 sets; one will be returned marked with the action taken.

- Maintain sets of Samples, as returned, at the Project site, for quality comparisons throughout the course of construction.

- Unless noncompliance with Contract Document provisions is observed, the submittal may serve as the final submittal.

- Distribution of Samples:  Prepare and distribute additional sets to subcontractors, manufacturers, Owner, fabricators, suppliers, installers and others as required for performance of the Work.  Show distribution on transmittal forms.

# 1.10	ARCHITECT'S ACTION

- Except for submittals for record, information or similar purposes, where action and return is required or requested, the Architect will review each submittal, mark to indicate action taken, and return promptly.

  - Compliance with specified characteristics is the Contractor's responsibility.

- Action Stamp:  The Architect will stamp each submittal with a uniform, self-explanatory action stamp.  The stamp will be appropriately marked to indicate the action taken.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION (Not Applicable)

# END OF SECTION 01300