Copyright 2002, The American Institute of Architects (AIA)

SECTION 01310

PROJECT MANAGEMENT AND COORDINATION

This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

GENERAL

RELATED DOCUMENTS

Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

SUMMARY

This Section includes administrative provisions for coordinating construction operations on Project including, but not limited to, the following:

Adjust list below to suit Project.

Coordination Drawings.

Administrative and supervisory personnel.

Project meetings.

Delete first paragraph below for projects conducted under a general construction contract.  If retaining paragraph for a project using multiple contracts, revise to suit local laws and regulations.  Some states and certain county and municipal jurisdictions prohibit assigning responsibility for coordination on a construction project to any contractor involved in Project.  This usually forces Owner, who is often the jurisdiction itself, or Architect, into construction-management activities.  Coordinate with Division 1 Section "Summary of Multiple Contracts."

Related Sections include the following:

List below only procedures that the reader might expect to find in this Section but are specified elsewhere.

Division 1 Section "Construction Progress Documentation" for preparing and submitting Contractor's Construction Schedule.

Division 1 Section "Execution Requirements" for procedures for coordinating general installation and field-engineering services, including establishment of benchmarks and control points.

Division 1 Section "Closeout Procedures" for coordinating Contract closeout.

COORDINATION

Requirements in this Article expand requirements in the General Conditions.  Delete if the General Conditions suit Project requirements and specific actions required.

Coordination:  Coordinate construction operations included in different Sections of the Specifications to ensure efficient and orderly installation of each part of the Work.  Coordinate construction operations, included in different Sections, that depend on each other for proper installation, connection, and operation.

Retain paragraph above for work performed under a single contract.  Retain first paragraph below for work performed under multiple contracts.  Coordinate with Division 1 Section "Summary of Multiple Contracts."

Retain subparagraphs below with either paragraph selected above.

Schedule construction operations in sequence required to obtain the best results where installation of one part of the Work depends on installation of other components, before or after its own installation.

Coordinate installation of different components with other contractors to ensure maximum accessibility for required maintenance, service, and repair.

Make adequate provisions to accommodate items scheduled for later installation.

Where availability of space is limited, coordinate installation of different components to ensure maximum performance and accessibility for required maintenance, service, and repair of all components, including mechanical and electrical. Coordinate location of pipes, conduits, ducts, light fixtures and similar items in confined areas to assure proper fit and access.  Contractor is responsible for handling interferences created by the work of subcontractors (example, sprinkler pipe interfering with installation of duct work; duct work interfering with installation of light fixtures). Coordinate spaces and clearances before fabrication of duct work and other shop fabricated items to assure proper size, configuration and fit of fabricated items.

Coordinate with contractors doing work for the Owner under separate contracts.

Prepare memoranda for distribution to each party involved, outlining special procedures required for coordination.  Include such items as required notices, reports, and list of attendees at meetings.

Prepare similar memoranda for Owner and separate contractors if coordination of their Work is required.

Administrative Procedures:  Coordinate scheduling and timing of required administrative procedures with other construction activities and activities of other contractors to avoid conflicts and to ensure orderly progress of the Work.  Such administrative activities include, but are not limited to, the following:

Insert other administrative activities below to suit Project.

Preparation of Contractor's Construction Schedule.

Preparation of the Schedule of Values.

Installation and removal of temporary facilities and controls.

Delivery and processing of submittals.

Progress meetings.

Preinstallation conferences.

Project closeout activities.

Startup and adjustment of systems.

Project closeout activities.

Conservation provisions in paragraph below may be difficult to enforce.  Penalties for wasteful practices, if necessary, are more enforceable if made a condition of the Contract and added by Supplementary Conditions.  Insert specific conservation requirements in appropriate Sections.

Conservation:  Coordinate construction activities to ensure that operations are carried out with consideration given to conservation of energy, water, and materials.

SUBMITTALS

Delete requirement for Coordination Drawings below if installation is completely shown on Shop Drawings.  Coordinate with individual Sections.  KEB – require coordination drawings only for complex projects.  Coordinate with MEP trades for requirements. 1.6 E.3 contains general coordination requirements by contractor and MEP trades.

Coordination Drawings:  Prepare Coordination Drawings if limited space availability necessitates maximum utilization of space for efficient installation of different components or if coordination is required for installation of products and materials fabricated by separate entities.

Content:  Project-specific information, drawn accurately to scale.  Do not base Coordination Drawings on reproductions of the Contract Documents or standard printed data.  Include the following information, as applicable:

Indicate functional and spatial relationships of components of architectural, structural, civil, mechanical, and electrical systems.

Indicate required installation sequences.

Indicate dimensions shown on the Contract Drawings and make specific note of dimensions that appear to be in conflict with submitted equipment and minimum clearance requirements.  Provide alternate sketches to Architect for resolution of such conflicts.  Minor dimension changes and difficult installations will not be considered changes to the Contract.

Revise first subparagraph below to establish a standard sheet size and format.

Delete requirement below for small projects.

Key Personnel Names:  Within 15 days of starting construction operations, submit a list of key personnel assignments, including superintendent and other personnel in attendance at Project site.  Identify individuals and their duties and responsibilities; list addresses and telephone numbers, including home and office telephone numbers.  Provide names, addresses, and telephone numbers of individuals assigned as standbys in the absence of individuals assigned to Project.

Post copies of list in Project meeting room, in temporary field office, and by each temporary telephone.  Keep list current at all times.

ADMINISTRATIVE AND SUPERVISORY PERSONNEL

Delete this Article for Project constructed under a general construction contract unless Project complexity requires additional provisions.  Requirements contained in the General Conditions for Project superintendents are sufficient for most projects.  Consult Owner's legal counsel before retaining this Article.

General:  In addition to Project superintendent, provide other administrative and supervisory personnel as required for proper performance of the Work.

Retain subparagraph below for multiple contracts.

Include special personnel required for coordination of operations with other contractors.

Insert special requirements that exceed requirements contained in the General and Supplementary Conditions for superintendent and assistants.

PROJECT MEETINGS

General:  Schedule and conduct meetings and conferences at Project site, unless otherwise indicated.

Attendees:  Inform participants and others involved, and individuals whose presence is required, of date and time of each meeting.  Notify Owner and Architect of scheduled meeting dates and times.

Agenda:  Prepare the meeting agenda.  Distribute the agenda to all invited attendees.

Minutes:  Record significant discussions and agreements achieved.  Distribute the meeting minutes to everyone concerned, including Owner and Architect, within three days of the meeting.

Delete paragraph and subparagraphs below if a preconstruction conference is not required.  If required, adjust number of days to suit Project.

Preconstruction Conference:  Schedule a preconstruction conference before starting construction, at a time convenient to Owner and Architect, but no later than 15 days after execution of the Agreement.  Hold the conference at Project site or another convenient location.  Conduct the meeting to review responsibilities and personnel assignments.

Revise first subparagraph below to suit Project.

Attendees:  Authorized representatives of Owner, Architect, and their consultants; Contractor and its superintendent; major subcontractors; suppliers; and other concerned parties shall attend the conference.  All participants at the conference shall be familiar with Project and authorized to conclude matters relating to the Work.

Agenda:  Discuss items of significance that could affect progress, including the following:

Add items to list below to suit Project.

Tentative construction schedule.

Phasing.

Critical work sequencing and long-lead items.

Designation of key personnel and their duties.

Procedures for processing field decisions and Change Orders.

Procedures for requests for interpretations (RFIs).

Procedures for testing and inspecting.

Procedures for processing Applications for Payment.

Distribution of the Contract Documents.

Submittal procedures.

Preparation of Record Documents.

Use of the premises.

Work restrictions.

Owner's occupancy requirements.

Responsibility for temporary facilities and controls.

Construction waste management and recycling.

Parking availability.

Office, work, and storage areas.

Equipment deliveries and priorities.

First aid.

Security.

Progress cleaning.

Working hours.

Minutes:  Record and distribute meeting minutes.

Include action items and responsible party.

Delete paragraph and subparagraphs below if Project does not require preinstallation conferences.  Limit preinstallation conferences to major assemblies if the Work requires tight control and coordination.  If necessary, individual Sections should specify preinstallation conferences as a requirement and should reference this Section.

Preinstallation Conferences:  Conduct a preinstallation conference at Project site before each construction activity that requires coordination with other construction.

Attendees:  Installer and representatives of manufacturers and fabricators involved in or affected by the installation and its coordination or integration with other materials and installations that have preceded or will follow, shall attend the meeting.  Advise Architect of scheduled meeting dates.

Agenda:  Review progress of other construction activities and preparations for the particular activity under consideration, including requirements for the following:

Delete unnecessary items from list below.  Add items to suit Project.

The Contract Documents.

Options.

Related requests for interpretations (RFIs).

Related Change Orders.

Purchases.

Deliveries.

Submittals.

Review of mockups.

Possible conflicts.

Compatibility problems.

Time schedules.

Weather limitations.

Manufacturer's written recommendations.

Warranty requirements.

Compatibility of materials.

Acceptability of substrates.

Temporary facilities and controls.

Space and access limitations.

Regulations of authorities having jurisdiction.

Testing and inspecting requirements.

Installation procedures.

Coordination with other work.

Required performance results.

Protection of adjacent work.

Protection of construction and personnel.

Record drawing process.

Record significant conference discussions, agreements, and disagreements, including required corrective measures and actions.

Reporting:  Distribute minutes of the meeting to each party present and to parties who should have been present.

Do not proceed with installation if the conference cannot be successfully concluded.  Initiate whatever actions are necessary to resolve impediments to performance of the Work and reconvene the conference at earliest feasible date.

Revise paragraph below if Project requires holding progress meetings at different intervals.  Insert special intervals such as "every third Tuesday" to suit special circumstances.

Progress Meetings:  Conduct progress meetings at weekly intervals.  Coordinate dates of meetings with preparation of payment requests.

Revise subparagraph below if attendance by other known entities is necessary.

Attendees:  In addition to representatives of Owner and Architect, each contractor, subcontractor, supplier, and other entity concerned with current progress or involved in planning, coordination, or performance of future activities shall be represented at these meetings.  All participants at the conference shall be familiar with Project and authorized to conclude matters relating to the Work.

Revise first subparagraph and associated subparagraphs below to suit Project.

Agenda:  Review and correct or approve minutes of previous progress meeting.  Review other items of significance that could affect progress.  Include topics for discussion as appropriate to status of Project.

Contractor's Construction Schedule:  Review progress since the last meeting.  Determine whether each activity is on time, ahead of schedule, or behind schedule, in relation to Contractor's Construction Schedule.  Determine how construction behind schedule will be expedited; secure commitments from parties involved to do so.  Discuss whether schedule revisions are required to ensure that current and subsequent activities will be completed within the Contract Time.

Review schedule for next period.

Review present and future needs of each entity present, including the following:

Adjust list below to suit Project.

Interface requirements.

Sequence of operations.

Status of submittals.

Deliveries.

Off-site fabrication.

Access.

Site utilization.

Temporary facilities and controls.

Work hours.

Hazards and risks.

Progress cleaning.

Quality and work standards.

Status of correction of deficient items.

Field observations.

Requests for interpretations (RFIs).

Status of proposal requests.

Pending changes.

Status of Change Orders.

Pending claims and disputes.

Record drawings.

Documentation of information for payment requests.

Minutes:  Record and distribute the meeting minutes.

Include action items and responsible party.

Reporting:  Distribute minutes of the meeting to each party present and to parties who should have been present.

Schedule Updating:  Revise Contractor's Construction Schedule after each progress meeting where revisions to the schedule have been made or recognized.  Issue revised schedule concurrently with the report of each meeting.

Paragraph and subparagraphs below are usually deleted, except for multiple contracts, because they are not needed.  Retain if Project is constructed under multiple contracts or if some unusual circumstance requires tighter control than normal.  Under multiple contracts, Owner often assigns responsibility for scheduling and conducting meetings to Project Coordinator.  Insert special intervals such as "every third Tuesday" to suit special circumstances.

Coordination/Progress Meetings:  Conduct Project coordination/progress meetings at regular intervals.  Project coordination meetings are in addition to specific meetings held for other purposes, such as progress meetings and preinstallation conferences.

Revise first subparagraph below if Project requires coordination meetings on a monthly or weekly basis.

Attendees:  In addition to representatives of Owner, each contractor, subcontractor, supplier, and other entity concerned with current progress or involved in planning, coordination, or performance of future activities shall be represented at these meetings.  All participants at the conference shall be familiar with Project and authorized to conclude matters relating to the Work

Agenda:  Review and correct or approve minutes of the previous coordination meeting.  Review other items of significance that could affect progress.  Include topics for discussion as appropriate to status of Project.

Combined Contractor's Construction Schedule:  Review progress since the last coordination meeting.  Determine whether each contract is on time, ahead of schedule, or behind schedule, in relation to Combined Contractor's Construction Schedule.  Determine how construction behind schedule will be expedited; secure commitments from parties involved to do so.  Discuss whether schedule revisions are required to ensure that current and subsequent activities will be completed within the Contract Time.

Schedule Updating:  Revise Combined Contractor's Construction Schedule after each coordination meeting where revisions to the schedule have been made or recognized.  Issue revised schedule concurrently with report of each meeting.

Review present and future needs of each contractor present, including the following:

Adjust list below to suit Project.

Interface requirements.

Sequence of operations.

Status of submittals.

Deliveries.

Off-site fabrication.

Access.

Site utilization.

Temporary facilities and controls.

Work hours.

Hazards and risks.

Progress cleaning.

Quality and work standards.

Change Orders.

Conduct coordination meetings with the mechanical, plumbing, sprinkler and electrical trades.  Before the trades start work in an area of the building, review structural clearances and locations of ducts, pipes, conduits, light fixtures, equipment and other items that affect location and proper fit.  Prepare coordination drawings where limited space availability necessitates maximum utilization of space for efficient installation of different components.  Verify depths and clearances before fabrication of ductwork.

Reporting:  Record meeting results and distribute copies to everyone in attendance and to others affected by decisions or actions resulting from each meeting.

Include action items and responsible party.

If special meetings such as site mobilization conferences or Project closeout conferences are required, insert articles here specifying meeting requirements.

PRODUCTS (Not Used)

EXECUTION (Not Used)

END OF SECTION 01310