Copyright 2002, The American Institute of Architects (AIA)

SECTION 01320

CONSTRUCTION PROGRESS DOCUMENTATION

This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

GENERAL

RELATED DOCUMENTS

Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

SUMMARY

This Section includes administrative and procedural requirements for documenting the progress of construction during performance of the Work, including the following:

Adjust list below to suit Project.

Preliminary Construction Schedule.

Contractor's Construction Schedule.

Submittals Schedule.

Adjust list below to suit Project.

Field condition reports.

Special reports.

Related Sections include the following:

Subparagraphs below include submittals usually specified in other Sections.  Revise to suit Project.

Division 1 Section "Payment Procedures" for submitting the Schedule of Values.

Division 1 Section "Project Management and Coordination" for submitting and distributing meeting and conference minutes.

Division 1 Section "Submittal Procedures" for submitting schedules and reports.

Division 1 Section "Quality Requirements" for submitting a schedule of tests and inspections.

SUBMITTALS

Coordinate first paragraph below with qualification requirements retained in "Quality Assurance" Article.

Qualification Data:  For scheduling consultant.

Submittals Schedule:  Submit three copies of schedule.  Arrange the following information in a tabular format:

Revise list below to suit Project.  Add information, such as scheduled dates for purchasing and installation and the activity or event number, if a CPM construction schedule is used.

Scheduled date for first submittal.

Specification Section number and title.

Submittal category (action or informational).

Name of subcontractor.

Description of the Work covered.

Scheduled date for Architect's final release or approval.

Preliminary Construction Schedule:  Submit two copies.

Contractor's Construction Schedule:  Submit two copies of initial schedule, large enough to show entire schedule for entire construction period.

Retain subparagraph below if required by Owner.

Field Condition Reports:  Submit two copies at time of discovery of differing conditions.

Special Reports:  Submit two copies at time of unusual event.

COORDINATION

Coordinate requirements in this Article with Part 2 "Submittals Schedule" Article.  If a submittal review sequence policy governs, revise this Article to comply with requirements.  See Evaluations for discussion on submittal review sequence policies.

Coordinate preparation and processing of schedules and reports with performance of construction activities and with scheduling and reporting of separate contractors.

Coordinate Contractor's Construction Schedule with the Schedule of Values, list of subcontracts, Submittals Schedule, progress reports, payment requests, and other required schedules and reports.

Secure time commitments for performing critical elements of the Work from parties involved.

Coordinate each construction activity in the network with other activities and schedule them in proper sequence.

PRODUCTS

SUBMITTALS SCHEDULE

Revise this Article to suit Project.  If there is an office submittal review sequence policy, insert specific requirements.  See Evaluations for discussion on submittal review sequence policies.

Preparation:  Submit a schedule of submittals, arranged in chronological order by dates required by construction schedule.  Include time required for review, resubmittal, ordering, manufacturing, fabrication, and delivery when establishing dates.

Coordinate Submittals Schedule with list of subcontracts, the Schedule of Values, and Contractor's Construction Schedule.

If a Preliminary Construction Schedule is not required, delete subparagraph below or revise to require initial submittal within 14 days of date established for commencement of the Work.

Initial Submittal:  Submit concurrently with preliminary bar-chart schedule.  Include submittals required during the first 60 days of construction.  List those required to maintain orderly progress of the Work and those required early because of long lead time for manufacture or fabrication.

Delete subparagraph below if not allowed.

Revise subparagraph below if schedule must be continuously updated to reflect current status and changes in timing for submittals.

Final Submittal:  Submit concurrently with the first complete submittal of Contractor's Construction Schedule.

CONTRACTOR'S CONSTRUCTION SCHEDULE, GENERAL

Manual referenced in first paragraph below contains basic recommendations for CPM procedures and methods.

Procedures:  Comply with procedures contained in AGC's "Construction Planning & Scheduling."

Time Frame:  Extend schedule from date established for commencement of the Work to date of  Final Completion.

Contract completion date shall not be changed by submission of a schedule that shows an early completion date, unless specifically authorized by Change Order.

PRELIMINARY CONSTRUCTION SCHEDULE

Delete this Article for small projects where time is not critical.  Retain it for larger or more complicated projects, even if Project requires CPM Contractor's Construction Schedule; coordinate with preliminary network diagram.  Preliminary Construction Schedule is not required by AIA Document A201; however, it is required by EJCDC Document 1910-8.  See Evaluations for discussion on optional dates below.

Bar-Chart Schedule:  Submit preliminary horizontal bar-chart-type construction schedule within seven days of date established for commencement of the Work .

Preparation:  Indicate each significant construction activity separately.  Identify first workday of each week with a continuous vertical line.  Outline significant construction activities for first 60 days of construction.  Include skeleton diagram for the remainder of the Work and a cash requirement prediction based on indicated activities.

CONTRACTOR'S CONSTRUCTION SCHEDULE

Gantt-chart schedule in this Article is adequate for many projects.  Delete this Article if Project size and complexity justify CPM construction schedule.  Time in first paragraph below usually needs extending for multiple contracts.

Schedule:  Submit a comprehensive, fully developed, horizontal Gantt-chart-type or CMP network analysis type, Contractor's Construction Schedule within 30 days of date established for commencement of the Work.  Base schedule on the Preliminary Construction Schedule and whatever updating and feedback was received since the start of Project.

REPORTS

Revise paragraph below to suit Project and special Owner requirements.

Field Condition Reports:  Immediately on discovery of a difference between field conditions and the Contract Documents, prepare and submit a detailed report.  Submit with a request for interpretation.  Include a detailed description of the differing conditions, together with recommendations for changing the Contract Documents.

SPECIAL REPORTS

Delete this Article on projects with only minimal requirements.

General:  Submit special reports to Architect within one day(s) of an occurrence.  Distribute copies of report to parties affected by the occurrence.

Retain paragraph below if Owner is unusually sensitive about public relations.

Reporting Unusual Events:  When an event of an unusual and significant nature occurs at Project site, whether or not related directly to the Work, prepare and submit a special report.  List chain of events, persons participating, response by Contractor's personnel, evaluation of results or effects, and similar pertinent information.  Advise Owner in advance when these events are known or predictable.

EXECUTION

CONTRACTOR'S CONSTRUCTION SCHEDULE

Retain first paragraph and subparagraphs below only for very complex projects of long duration.

Contractor's Construction Schedule Updating:  At monthly intervals, update schedule to reflect actual construction progress and activities.  Issue schedule one week before each regularly scheduled progress meeting.

Revise schedule immediately after each meeting or other activity where revisions have been recognized or made.  Issue updated schedule concurrently with the report of each such meeting.

Include a report with updated schedule that indicates every change, including, but not limited to, changes in logic, durations, actual starts and finishes, and activity durations.

As the Work progresses, indicate Actual Completion percentage for each activity.

Distribution:  Distribute copies of approved schedule to Architect, Owner, separate contractors, testing and inspecting agencies, and other parties identified by Contractor with a need-to-know schedule responsibility.

Post copies in Project meeting rooms and temporary field offices.

When revisions are made, distribute updated schedules to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in performance of construction activities.

END OF SECTION 01320