SECTION 01300

SUBMITTALS, MEETINGS AND RECORD DOCUMENTS

1. 	GENERAL

1.1	PRE-CONSTRUCTION MEETING

A. 	Architect will schedule a pre-construction meeting within 15 days of issuance of Notice 		to Proceed, to be attended by the owner, all project managers, Contractor's field 				superintendent, and representatives of major sub-contractors.  At this time, Contractor 		shall make specified pre-construction submittals including following:

1. 	Typed list of sub-contractors with addresses and telephone numbers.

2.  	Certificates of insurance.

3.  	Approved construction schedule.  See General Conditions, Paragraph 3.10.

4.  	Schedule of values.

5.  	Start-up authorization or certificates.

B.  	Pre-construction meeting agenda will include following:

1.  	Processing application for payment.

2.  	Processing and distribution of submittals.

3.  	Maintenance of record documents.

4.  	Procedure for field changes, change estimates, change orders, etc.

5.  	Site and building security.

6.  	Location and maintenance of temporary storage areas, field offices, vehicular 				parking and access, waste disposal, etc.

7.  	Safety and first-aid procedures.

8.  	Date and time for regular monthly coordination and progress meeting (to be 					coordinated with monthly application for payment).

1.2 	CONSTRUCTION SCHEDULE

A.  	Refer to General Conditions, Paragraph 3.10, for general provisions concerning 				construction progress schedule.  Schedule shall show activities, itemized according to 		specification Section, and be organized in bar-chart or graph form so as to show both 			projected and actual progress of work.

B.  	Arrange schedule to indicate required sequencing of  units, and to show time allowances 		for submittals, inspections, and similar time margins.

C.  	Show critical submittal dates related to each time bar, or prepare a separate coordinated 		listing of critical submittal dates.

D.  	Show phases of work within each time bar for major elements which involve purchase 		lead-time, fabrication, seasonal treatment, mockups, testing, or similar phases as well as 		installation.

E. 	Submit updated schedule monthly, together with application for payment.

1.3 	SCHEDULE OF VALUES

A.  	Refer to General Conditions, Paragraph 9.2 for general provisions concerning schedule 		of values.

B. 	For these submittals, use AIA Document G702/703, Application and Certificate for 			Payment.

C. 	Use specifications Sections as listed in Table of Contents as basis for format for listing 		costs.

D. 	Itemize separately general cost items, such as bonds and allowances.

E.  	Itemize change orders separately as they are approved.

1.4 	MEETINGS AND REPORTING

A. 	Contractor shall conduct general progress and coordination meetings at least once each 		month, attended by a representative of each primary entity engaged for performance of 		work.  Record discussions and decisions, and distribute copies to those attending and 			others affected, including Architect/Engineer.

B. 	Date and time of at least one regular monthly progress and coordination meeting shall 		be determined at the pre-construction meeting.  Timing of this monthly meeting shall be 		coordinated with payment requests.

1.5 	APPLICATION FOR PAYMENT

A.	Refer to General Conditions, Paragraph 9.3, for general provisions concerning 				applications for payment.

B. 	Use AIA Form G702/703, fully completed and executed.

C. 	Submit the forms in triplicate including attachment of waivers and similar 					documentation with one copy.

1.6 	SHOP DRAWINGS, PROJECT DATA, SAMPLES

A. 	Refer to General Conditions, Product Data and Samples, paragraph 3.12, for general 			provisions covering this type of submittal.

B. 	Coordinate the preparation and processing of work-related submittals with the 				performance of the work.  Coordinate each separate submittal with other submittals and 		related activities that require sequential activity.  Coordinate the submittal of different 		units of interrelated work so that one submittal will not be delayed by the necessity of 			reviewing a related submittal.

C. 	Architect/Engineer Review:

1. 	Allow ten working days for the Architect/Engineer's initial processing of each 				submittal.  Allow one  week for reprocessing each submittal.  No extension of time 			will be authorized because of failure to transmit submittals to the 							Architect/Engineer sufficiently in advance of the work.

2. 	The Architect/Engineer will stamp each submittal to be returned with a uniform, 			self-explanatory action stamp, appropriately marked and executed to indicate the 			status of the submittal.

D.  	Mark each submittal with a permanent label for identification.  Provide project name, 			date, name of Architect/Engineer, name of Contractor, number and title of appropriate 		specification section and similar definitive information.  Provide a space on the label for 		Contractors and Architect/Engineer's review markings.

E.  	Package each submittal appropriately for transmittal and handling.  Send each submittal 		from the Contractor to the Architect/Engineer and other destinations using AIA 				Transmittal  Form G810.

F.  	Provide additional copies of submittals required by governing authorities that are in 			addition to copies specified for submittal to the Architect/Engineer.

G. 	Where it is necessary to provide intermediate submittals between the initial and final 			submittals, provide and process intermediate submittals in the same manner as for initial 		submittals.

H.  	Submit as follows:

1.  	Shop drawings (original drawings prepared by Contractor or sub-contractor 					illustrating fabrication, layout, erection details, etc.): six prints, or one reproducible 			transparency and one opaque print, to Architect.

2.  	Manufacturers' specifications, installation instructions, charts, schedules, catalogs, 			brochures, etc.:  number of copies required by Contractor for distribution, plus one 			copy for Architect's retention.

3.  	Samples:  one sample to Architect only, unless otherwise specified.

4.  	In submitting shop drawings and product data to Architect, use separate transmittals 			for material in different specification Sections, with applicable specification 					Section clearly numbered.

I.  	Architect will review submittals within ten working days, measured from date of receipt 		by Architect until date of mailing.  Contractor shall promptly make corrections and 			resubmit when so directed.  Where submittal is marked "Approved as Noted" or similar, 		assume that all items are approved other than those to which specific exception is taken.  		Do not delay fabrication, assembly and delivery pending receipt of entirely "Approved" 		submittal.

J.  	Distribute approved submittals to job site and record document files, and to suppliers 			and sub-contractors as required.  Samples not designated by Contractor for 					incorporation into Work shall be kept on file until job completion.  Any sample not 			reclaimed within 30 days after job completion will be considered unclaimed, and will be 		disposed of as directed by Architect.

1.7 	PROJECT RECORD DOCUMENTS

A.  	Keep on file at job site one complete set of up-to-date Contract Documents, including 		drawings and specifications, addenda, shop drawings and product data, testing data, 			change orders, field orders, and other modifications.  Documents shall be neatly and 			securely stored in files or on racks, clearly indexed by trade activity or specification 			Section, and shall not be used for construction purposes.

B. 	Legibly mark significant field changes such as following, using colored pencils or felt-			tipped pens:

1.  	Drawings:  locations of concealed utilities, field changes of dimension and detail, 				changes resulting from change order or field order, and details not on original 				drawings.

2.  	Specifications:  manufacturer and model number of equipment actually installed.

3.  	Shop drawings and manufacturers' literature:  changes made after Architect's 				review.

C.  	At completion of Work, deliver completed record documents to Architect.  Final 				payment for Project will not be made until Architect reviews and approves these 				documents.

1.8 	SUBSTANTIAL COMPLETION

A.  	Refer to General Conditions, Article 9, Substantial Completion, for general provision 			concerning substantial Completion.

B.  	Following issuance by Architect/Engineer of Certificate of Substantial Completion, 			Contractor may submit special payment request, provided the following have been 			completed:

1.  	Obtain permits, certificates of inspection and other approval and releases by 					governing authorities, required for Owner's occupancy and use of project.

2.  	Submit warranties and similar documentation.

3. 	Submit maintenance manuals and provide instruction of Owner's 							operational/maintenance personnel.

4.  	Complete final cleaning of the work.

5.  	Submit record documents.

6.  	Submit listing of work to be completed before final acceptance.

C.  	Following completion of the following requirements, final payment request may be 			submitted:

1.  	Complete work listed as incomplete at time of substantial completion, or otherwise 			assure Owner of subsequent completion of individual incomplete items.

2.  	Settle liens and other claims, or assure Owner of subsequent settlement.

3.  	Submit proof of payment on fees, taxes and similar obligations.

4.  	Transfer operational, access, security and similar provisions to Owner; and remove 			temporary facilities, tools and similar items.

5.  	Completion of requirements specified in "Project Closeout" section.

6.  	Obtain consent of surety for final payment.

END OF SECTION