***MMC East Tower and Visitors Garage Overbuild Site Plan - including CMP and Detours for Congress Street Closure***

 *3.21.2018* ***draft POTENTIAL CONDITIONS OF APPROVAL Shared with MMC***

|  |  |
| --- | --- |
| **SUBJECT** | **PROPOSED CONDITION TEXT** |
| **Final documentation of land transfers** | That the documentation of the land transfers and street acceptances associated with the sites shall be completed prior to the certificate of occupancy. |
| **FAA approvals** | That the applicant shall submit evidence from the FAA that the location and height of the construction equipment, the overbuild heights, and helipad relocation is acceptable prior to the certificate of occupancy for the approved overbuild floor area, or the operation of equipment and helipad. |
| **Design**  | [under discussion] |
| **TDM** | That the applicant shall finalize a *TDM Plan* that addresses the Regulatory Framework and Site Plan requirements, for review and approval by the Planning Board within 6 months of the date of this approval.  |
| **Pedestrian Integration and CPTED** | That the applicant shall develop a long term public *Pedestrian Network Plan* showing the integration of the upper level MMC campus with the Congress Street corridor, including measures to address CPTED principles, for implementation when the retail units beneath the Visitors Garage are available for lease or sale; such plan to be submitted for review and approval prior to the issuance of a certificate of occupancy for the Visitors Garage. |
| **Helipad Relocation impacts** | That within 9 months of the date of this site plan approval the applicant shall submit a “*Sound Measurement Plan*” for review and approval by the Planning Authority, for assessing the actual changes in sound impacts on nearby properties between the helipad operating at the existing site and at the new location, including criteria for mitigation where such impacts are severe based on appropriate national standards. The “*Sound Measurement Plan*” is required in the event that the predicted sound levels are incorrect, and it shall be approved and implemented at least 2 months before the helipad is relocated. |
| **Construction Management Plan – actons affecting ROW** | That the applicant and its agents shall undertake all construction associated with this site plan in accordance with the CMP dated XXX and Detour Plan (MOT) dated XXX unless agreed in writing with Planning Authority, including: (the final list depends on what is in todays submissions, which are under review)* Provision of alternative parking for any parking displaced by the construction either on or off the MCC campus; and
* Coordination with the Seadogs and other event organizers, and with METRO, to ensure safety of all users; and
* Ongoing monitoring and adjustments in consultation with city representatives
* Park and Weymouth signal should meet Maine UTCD requirements and include pedestrian accommodations, ADA compliance and have full vehicle detection
* Minor ROW adjustments such as curb radii at Boynton/Forest Streets, ADA ramps and bus stop pads
* Weymouth repave requirements
* Others?
 |
| **SUBJECT** | **PROPOSED CONDITION TEXT** |
| **Construction Management Plan- responsibility** | That the applicant is solely responsible for all activities (physical modification to the ROW, monitoring, revisions to the CMP etc) associated with CMP/detour plans referred to in condition X above. |
| **Construction Management Plan – impacts/communication**  | That the applicant shall ensure that construction impacts are minimized for neighbors, including businesses, in the vicinity of the project, and implement the Communications Plan generally as outlined. |
| **Construction Management Plan – penalties for delay** | That the applicant shall comply with the submitted Construction Schedule which confirms that Congress Street will be closed between Monday May 7th to Thursday, June 28th inclusive. If Congress Street is not open to two-way through traffic (cars and pedestrians) on June 29th, the Planning Board recommends that that penalties of $XXX/day should apply for each day of delay. |
| **Stormwater Management Plan** | That the stormwater system for the MMC Bramhall Street/ Congress Street expanded campus shall add detention capacity in lieu of stormwater separation in order to reduce the burden of the existing & proposed development on the City’s infrastructure. The applicant shall set out [timetable still under discussion], the strategy & associated proposals for achieving substantial additional detention or for contributions to other measures that achieve the same objective. |
| **Retail uses of units under VG** | That the applicant shall submit a strategy ensuring the space on Congress Street beneath the Visitors Garage is occupied as soon as Turners vacates the space, to be coordinated with the *Pedestrian Network Plan* subject of condition X above; such strategy to be submitted for review and approval prior to the issuance of a certificate of occupancy for the Visitors Garage. |
| **Design of new signs**  | That any new signage relating to the East Tower or Visitors Garage shall be subject to separate site plan review by the Planning Authority prior to installation. |
| **ROW including Street Lights** | That the applicant shall implement the following upgrades in the ROW:* update the four (4) pedestrian light fixtures along the Congress Street frontage of the Visitors Garage to LED, and for each add the bracket and LED light fixture at the top of the existing poles.
* Install ADA pedestrian ramps at 4 locations where there are crosswalks near the East Tower
 |
| **Parking** | That the final parking layout of the Visitors Garage shall meet the City’s Technical Manual Standards and all applicable State and Federal standards regarding handicap accessibility. |
| **Bicycle parking** | That the applicant shall submit an assessment of the existing bicycle parking near the East Tower to confirm whether it meets the City’s Technical Standards for the location, number and design of bicycle parking to serve the East Tower as expanded, and add to/relocate or replace bicycle parking as necessary to meet the standards prior to the issuance of a certificate of occupancy for the East Tower. |
| **Capacity letters** | That the applicant shall submit the ability to serve letters regarding water and wastewater prior to the issuance of a building permit for the East Tower overbuild. |