TDM Planning Meeting, Monday, June 1, 2009

Attending: Jean Fraser, Bill Needleman, Tom Errico and Judy Harris

Discussed process issues and devised preliminary plan.

- Judy will contact Steve Hobart at Maine Med and ask for whatever materials they have completed. Staff will review materials before mid-July meeting with Hobart.

Goal: MMC materials ready for August PB workshop and September PB hearing.

- Jean will coordinate dates with Barbara B.

- Judy will submit preliminary process proposal to staff and Go Maine prior to 6/19/09 for their review. JHH will be away until July 13th.

- Staff will meet to agree upon process – late July

- Planning Staff will research Parking in-lieu fees and impacts*

- Planning Staff will review developer tenant relationship/leases*

- Tom will suggest standards for traffic counting, parking etc.*

- Molly Castro et al will complete standards by end of July*

- JHH suggests monthly staff TDM meetings – should include PS dept. and parking.

*Items 5-8 should be circulated prior to the end of July process meeting.

Stages of TDM Process

Stage 1		Outreach to business community

Responsibility: JHH, Greg Mitchell and staff

Stage 2		Planning Dept meeting with Developer

Transfer of info

Responsibility: Planning Staff

Stage 3		Referral to Go Maine and Plan development

Stage 4		Review

Planning and JHH

Stage 5		Presentation to PB

Planning

Stage 7		Approval and initial monitoring

PB and JHH

Current email list shall be expanded as process develops.