Draft Transportation Demand Management Plan

Portland Bramhall Campus

January 2008

Project Background

The City of Portland required that MMC complete a travel/transportation demand management plan as a condition of their site plan approval for the most recent expansion to be completed in the summer of 2008.  The purpose of this plan is to reduce the impact of the traffic associated with MMC on the area’s roadway network.

Draft Plan

Gorrill-Palmer Consulting Engineers Inc. worked with Maine Medical Center over the past several months to prepare this Draft Transportation Demand Management plan.  This initial plan which will be updated annually will focus primarily on rideshare and Metro since MMC indicates they are most likely to have the greatest reduction at least initially.  We present each major component of the plan including a discussion of the approach, followed by action items for each component of the plan.

Appoint  a Transportation Coordinator

This will be a part time position in the Parking Department.  This coordinator will be responsible for working with the City of Portland staff, Portland Area Comprehensive Transportation Committee (PACTS), and the MaineDOT with respect to the following:

- Rideshare

- Public transportation availability

- Transit routes

- MMC work schedules vs transit schedule

- Park and ride programs

- Biking and pedestrian opportunities and issues

- Educate and coordinate with the MMC community on TDM opportunities and work with them to promote TDM

- Monitor the successes and challenges of the program

- Conduct a survey of the MMC commuters to gain input on what is working and what measures would encourage more participation

- File an annual report for review by the staff, management and the City.  While the initial goal will be to reduce the number of single occupant vehicles during the initial year by 2%, the transportation coordinator will need to update these goals in subsequent years.

The work to be completed by the transportation coordinator during the first year will include the following:

- Prepare educational/promotional material for employees to highlight the goals of the plan and their participation, the desired outcomes, and to obtain their thoughts and suggestions.  Emphasize an “open door” policy with respect to continued feedback and suggestions for the program.

- Prepare transportation survey of the staff to obtain information on how people currently travel to and from MMC, whether they would consider alternatives to the single occupant vehicle and what type of programs/incentives would make them more likely to participate in this program.

- Work with the employees to implement a rideshare database and rideshare program.

- Actively participate in regional planning agencies by volunteering to be on the advisory committees for the Portland Peninsula Transit Study which will begin in January of 2008, the Portland Metro Regional Route study which will begin soon, volunteering to serve on other committees as appropriate such as the PACTS transit committee, attending the annual transit summit and other meetings as appropriate.

- Monitor and keep records of the participation in the transportation initiatives outlined below.

- File an annual report with the City of Portland in June of 2009 and share the report with MMC management and staff.

Implement Rideshare/Vanpool Program

This program will include a database program for matching rideshare candidates and will be administered by the Transportation coordinator.   The initial step will be to develop an employee survey of the staff to obtain information on how people currently travel to and from MMC, whether they would consider alternatives to the single occupant vehicle and what type of programs/incentives would make them more likely to participate in this program.  MMC will encourage employee participation in the plan by offering preferential parking or possibly free parking in the garage or other incentive(s) to be identified, and a guaranteed ride home by a contract with a local taxi service or some alternative preferred service.  An important feature of this program is for the transportation coordinator to monitor participation on a periodic basis.  This program may also be coordinated with the Greater Portland Council of Governments regional rideshare program.  During the next year, the transportation coordinator will work with MMC management to evaluate whether it is feasible to maintain a vehicle fleet for use by employees for offsite meetings and to facilitate the guaranteed ride home program by participants in future years of the plan.

Encourage Use of Transit

The Greater Portland Area is fortunate to have a variety of transit alternatives including Metro, the South Portland Bus Service, Zoom, The Downeaster and others.  We recommend that MMC encourage the use of this alternative by displaying updated schedules prominently and promoting their use by offering discounted monthly bus passes to their employees.  The locations of the bus stops will be reviewed with Metro to see if any changes should be made to make it more welcoming.   As previously mentioned in this plan, The Portland Area Comprehensive Transportation Committee (PACTS) in coordination with the City of Portland, is just undertaking a Peninsula Transit Study as well as a routing study which would benefit from the active participation of MMC.  The outcomes of the PACTS studies will include a determination of feasible transit alternatives and associated facilities in the region, as well as routes, and timings.  In the coming year, MMC will review their shift time with the transit route schedules which are developed to see if it is appropriate or feasible to make any changes.

Promote a Bicycling and Walking Program

For those commuters who live within five miles, bicycling or walking to work should be encouraged though provisions of secure bicycle racks in a nice, welcoming, well lit and protected area.  We recommend that MMC investigate the possibility of providing lockers and showers at the site and consider other incentives such as those described earlier or perhaps an annual drawing for a new bicycle.