| ##### FIELD REPORT #14 SRG Engineering, Inc. P. O. Box 925 Gray, ME 04039-0925 ### Tel :(207)-657-7323 Fax :(207)-657-7342 | Project No.:07-003 Date: July 10, 2007 Project Name: Mercy Hospital Project Location: Portland, Maine Weather Conditions: Overcast, occ’l light mist Contact Person(s): Steven Grant-SRG Eng. |
| --- | --- |
| Discussion/Observations: (All Levels) | Copies To: Sean Welty-KLMK Roger Domingo-SWC James Lanza-Gilbane Paul Stevens-SMRT Janusz Wszola (EOR)-SMRT Cathy Streifel-SMRT |
| Comments: - Structural Steel: Please refer to Quality Assurance Lab reports for items needed to be addressed by contractor. Mullions at Penthouse floor not anchored to concrete curb at Line 2. Action Required: Contractor to complete fastening per contract documents. Concrete curb at Line 4 not in place yet. - Exterior Wall Board: In place at line A and 1, partially in-place at line 4.7 along 3rd floor level. No masonry anchor ties in-place yet. - Masonry Veneer: Just starting to place at Line 1. - Miscellaneous Steel: Seismic clips at top of interior masonry walls not in-place. Action Required: Contractor to provide per contract documents. |  |
| Diagrams: (Attached Photos 1 through 21) |  |
| C: File | Signed: ___________________________________ |

- 1 of  1-