## TOC
SUMMIT GEOENGINEERING SERVICES
434 Cony Road, Augusta, Maine 04330
Tel: (207) 621.8334 Fax: (207) 626.9094
TABLE OF CONTENTS
PROJECT NO: |  | 14063
PROJECT NAME: |  | UNE College of Pharmacy
CLIENT: |  | University of New England
DATE | WORK ACTIVITY/LOCATION
2008-05-14 | Concrete testing footings and foundation
2008-05-15 | Cylinder pickup set #'s 2 and 3
2008-05-27 | Concrete testing North and West side foundation wall
2008-05-29 | Concrete tesing footing foundation and cylinder pickup # 4 and 5
2008-05-30 | Cylinder pickup Set #6
2008-06-13 | Concrete testing foundation walls
2008-06-16 | Cylinder pickup sets 7 and 8
2008-06-20 | Concrete testing elevator pit floor
2008-06-23 | Cylinder pickup set 9
2008-07-03 | Concrete testing for wall
2008-07-07 | Cylinder pickup set 10
2008-07-10 | Concrete testing
2008-07-11 | Cylinder pickup set 11
2008-07-18 | Concrete test, # 12
2008-07-31 | Concrete test and cylinder pickup #12
2008-08-01 | Cylinder pickup #13
2008-08-20 | Concrete testing
2008-08-21 | Cylinder pickup #14
2008-08-22 | Concrete testing services
2008-08-28 | Concrete testing services
2008-08-29 | Cylinder pickup sets 17, 18, and 19
2008-09-09 | Concrete testing services
2008-09-10 | Concrete testing and cylinders pick up
2008-09-15 | Concrete testing services
2008-09-16 | Cylinders pick up
2008-09-29 | Mortar and Grout Sampling
2008-09-30 | Mortar and Grout Pick Up
2008-11-11 | Concrete testing
2008-11-26 | Mortar and Grout Pick Up
2008-12-01 | Mortar and Grout Pick Up
2009-01-09 | Sprayed Resistive Fire proofing Inspection Basement Level
2009-01-12 | Sprayed Resistive Fire proofing Inspection Basement Level

## Template
DAILY FIELD REPORT
Date:
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses | Signed:
Leave: |  | Mileage: | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: |  | Density Gauge: |  | Tom Melican, John B. Sullivan Corp.
TOTAL: |  | Other:
|  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:

## Density Results Summary
SUMMIT GEOENGINEERING SERVICES
434 Cony Road, Augusta, Maine 04330
Tel: (207) 621.8334 Fax: (207) 626.9094
SUMMIT GEOENGINEERING FIELD DENSITY RESULTS SUMMARY
PROJECT NO: |  | 14063
PROJECT NAME: |  | UNE College of Pharmacy
CLIENT: |  | University of New England
Test Number | Date | Location: | Lift Elevation | Moisture Content % | In-place Density DD PCF | Maximum Density PCF | Percent Compaction | Required Compaction | Remarks
Remarks:
Proctor Information:

## 1-12-09
DAILY FIELD REPORT
Date: | 2009-01-12
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Darrell Gilman
Leave: | 9:00 | Mileage: | 120 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 11:15 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.25 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2009-01-16
A crew from New England Fire Proofing is placing Grace product Monokote Z-106/HY medium density SFRM for the required structural members and assemblies as shown on drawings S1.2 (beams & decking), and S1.7 & S1.8 (Columns & Braces) of the structural drawings. UL fire resistive design thicknesses for columns, beams, braces, and decking are supplied by the approved submittal information from New England Fireproofing dated 12-9-08. Application is rated for 2 hours areas with 1/2 flange tip thickness. SFRM is being applied to unprimed structural steel. The SFRM is being inspected for proper thickness, density, and bond strength as required in project specification section 078100 part 3.5C.
Inspection of the Sprayed Fire Resistive Material (SFRM) for the basement level structural members.
Bond Strength: SFRM has checked at the rate of one test per 10,000 sq. ft. of area for the rated beams, columns, and decking. Results: 805psf to 1059psf Required: 434psf Density: Wet Density: 46.6pcf, (38-43 pcf recommended) Dry Density: 30.5pcf (22 pcf minimum required)

## 1-9-09
DAILY FIELD REPORT
Date: | 2009-01-09
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Darrell Gilman
Leave: | 9:00 | Mileage: | 120 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.75 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2009-01-16
A crew from New England Fire Proofing is placing Grace product Monokote Z-106/HY medium density SFRM for the required structural members and assemblies as shown on drawings S1.2 (beams & decking), and S1.7 & S1.8 (Columns & Braces) of the structural drawings. UL fire resistive design thicknesses for columns, beams, braces, and decking are supplied by the approved submittal information from New England Fireproofing dated 12-9-08. Application is rated for 2 hours areas with 1/2 flange tip thickness. SFRM is being applied to unprimed structural steel. The SFRM is being inspected for proper thickness, density, and bond strength as required in project specification section 078100 part 3.5C.
The SFRM is being allowed to dry prior to bond strength testing on Monday.
Inspection of the Sprayed Fire Resistive Material (SFRM) for the basement level structural members.
Thickness: SFRM has checked at the rate of not less than 25% of the rated beams and columns, and decking at one check per 1,000 sq.ft. of area. All areas tested met the require thickness. Density and bond strength are to be completed on 1-12-09.

## 12-1-08
DAILY FIELD REPORT
Date: | 2008-12-01
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 9:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-12-08
Picked up mortar and grout (#M2 AND G2) for compressive strength testing and controlled storage.
Mortar and Grout Pickup
NA

## 11-26-08
DAILY FIELD REPORT
Date: | 2008-11-26
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 11:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-12-01
Collected mortar sample (14063-M2), and also Grout (14063-G2) during the placement of the second floor elevator wall.
Mortar and Grout Sampling
Grout Temp.: 58 deg. F. Slump: 8 1/2" Mortar: Temp.: 59 deg. F.

## 11-12-08
DAILY FIELD REPORT
Date: | 2008-11-12
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Neil Davis
Leave: | 1:00pm | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 2:15pm | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1.25 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-11-14
Picked up three sets of four cylinders for compressive strength testing and controlled storage.
Cylinder Pickup
NA

## 11-11-08
DAILY FIELD REPORT
Date: | 2008-11-11
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Mike Sullivan
Leave: | 6:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-11-13
A crew from Pride Concrete Floor placed a total of 195 cy for the basement floor slab. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with glenium, (mid-range water reducer) fibermesh & pozzutec20 ( polar set) added at the batch plant. The concrete was placed via pump. Three sets of four test cylinders were cast and will be picked up at a later date for lab testing and controlled storage.
Concrete Testing Services.
Slump: 5" to 6 1/2 " Air content: 3.2% to 8% Concrete Temperature: 56 to 60 deg. F. Air Temperature: 35 deg. F Three sets of four cylinders were cast for compressive strength testing.

## 9-30-08A
DAILY FIELD REPORT
Date: | 2008-09-30
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 9:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-10-07
Picked up mortar and grout (#M1 AND G2) of four cylinders each for compressive strength testing and controlled storage.
Mortar and Grout Pickup
NA

## 9-16-08
DAILY FIELD REPORT
Date: | 2008-09-16
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 11:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-09-22
Picked up one set (#27) of four cylinders for compressive strength testing and controlled storage.
Cylinder Pickup
NA

## 9-15-08
DAILY FIELD REPORT
Date: | 2008-09-15
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 7:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-09-22
A crew from Pride Concrete Floors placed a total of 14 cy for the attic equipment deck. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Glenium (mid-range water reducer) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 5 1/2" Air content: 2.4% Concrete Temperature: 81deg. F. Air Temperature: 70 deg. F One set of four cylinders was cast for compressive strength testing.

## 9-11-08
DAILY FIELD REPORT
Date: | 2008-09-11
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Picked up three sets (#23,24,25,&26) of four cylinders each for compressive strength testing and controlled storage.
Cylinder Pickup
NA

## 9-10-08
DAILY FIELD REPORT
Date: | 2008-09-10
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 6:30am | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 1:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
A crew from Pride Concrete Floor placed a total of 170 cy for the third floor slab. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Glenium (mid-range water reducer) added at the batch plant. The concrete was placed via pump. Also pick up three sets of four cylinders for compressive strength testing.
Concrete Testing Services.
Slump: 6-3/4" to 7-1/4 " Air content: 2.4% to 3% Concrete Temperature: 72 to 74 deg. F. Air Temperature: 60 to 70 deg. F Four sets of four cylinders were cast for compressive strength testing.

## 9-9-08
DAILY FIELD REPORT
Date: | 2008-09-09
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Neil Davis
Leave: | 6:15am | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 11:45am | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 5.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-09-10
A crew from Pride Concrete Floor placed a total of 140 cy for the second floor slab. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 5-3/4" to 7-1/2 " Air content: 2.0% to 2.4% Concrete Temperature: 73 to 76 deg. F. Air Temperature: 73 to 75 deg. F Three sets of four cylinders were cast for compressive strength testing.

## 8-29-08
DAILY FIELD REPORT
Date: | 2008-08-29
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 3:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 5:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-09-02
Picked up three sets (#17,18,&19) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinder Pickup
NA

## 8-28-08
DAILY FIELD REPORT
Date: | 2008-08-28
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 6:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-09-02
A crew from Pride Concrete Floor placed a total of 150 cy for the first floor slab. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 5 1/4" to 8" Air content: 2.6% to 3% Concrete Temperature: 75.5deg. F. Air Temperature: 77deg. F three sets of four cylinders were cast for compressive strength testing.

## 8-25-08
DAILY FIELD REPORT
Date: | 2008-08-25
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 10:00/1:00 | Mileage: | 10 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:30/6:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Performed a shear stud inspection for the first, second, and third floor frame as shown on S-1.2 thru S-1.4 of the structural drawings.
Shear Stud inspection
All area inspected pass but line A.5 on second floor, from 3.6 to 4 and line D.5 on third floor, from 3 to 4

## 8-22-08
DAILY FIELD REPORT
Date: | 2008-08-22
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 10:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 2:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 4 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-25
A crew from Coastal Concrete placed a total of 48.5 cy for the South area way and loading dock footing. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 3 1/2" to 5 1/2" Air content: 4.7% Concrete Temperature: 78deg. F. Air Temperature: 65deg. F One set of four cylinders was cast for compressive strength testing.

## 8-21-08
DAILY FIELD REPORT
Date: | 2008-08-21
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Picked up two sets (#14&15) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinders Pickup
NA

## 8-20-08
DAILY FIELD REPORT
Date: | 2008-08-20
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 6:45 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 1:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.25 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
A crew from Pride Concrete Floor placed a total of47 cy for the attic slab, and a crew from Coastal Concrete placed a total of 10cy for the piers on line 4-A. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump. For the attic slab mix # 2 was used with no air, and mix # 1 for the piers with air.
Concrete Testing Services.
Slump: 5" Slump: 5 1/2" Air content: 2.3% Air content: 5.5% Concrete Temperature: 75.5deg. F. Concrete temp.: 75 Air Temperature: 60deg. F Two sets of four cylinders was cast for compressive strength testing.

## 8-01-08
DAILY FIELD REPORT
Date: | 2008-08-01
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 9:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-01
Picked up two sets (#13) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinder Pickup
NA

## 7-31-08
DAILY FIELD REPORT
Date: | 2008-07-31
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 11:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 17:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-01
A crew from Coastal Concrete placed a total of 52.5 cy for the South area footing, the North area way wall, North masonry pier, pier G 3.6, and entry foundation wall on the East side. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump. Also, picked up cylinder set # 12 cast on 7-18-08
Concrete Testing Services.
Slump: 4" to 5-1/2" Air content: 5.8% Concrete Temperature: 85deg. F. Air Temperature: 80deg. F One set of four cylinders was cast for compressive strength testing.

## 7-18-08
DAILY FIELD REPORT
Date: | 2008-07-18
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Frank Clark
Leave: | 11:15am | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 2:00pm | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.75 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
A crew from Coastal Concrete placed a total of 12.5 cy for the wall on line A from 1 to 2 and the 1' wall around the stairway in the basement.. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with a MRWR ( Glenium ) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 3 3/4" to 5-3/4" Air content: 4.5 to 4.8% Concrete Temperature: 85 to 87 deg. F. Air Temperature: 98 deg. F One set of four cylinders was cast for compressive strength testing.

## 7-11-08
DAILY FIELD REPORT
Date: | 2008-07-11
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 7:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 8:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
Picked up two sets (#11) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinder Pickup
NA

## 7-10-08
DAILY FIELD REPORT
Date: | 2008-07-10
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 1:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
A crew from Coastal Concrete placed a total of 8 cy for footing B2.4, stair A wall, and stair B footing. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid-range water reducer.
Concrete Testing Services.
Slump: 5 1/2" Air content: 5.5% Concrete Temperature: 85 deg. F. Air Temperature: 80 deg. F One set of four cylinders was cast for compressive strength testing.

## 7-7-08
DAILY FIELD REPORT
Date: | 2008-07-07
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 10:00 | Mileage: | 4 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 11:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-10
Picked up two set (#10) of four cylinders each for compressive strength testing.
None
Cylinder Pickup
NA

## 7-3-08
DAILY FIELD REPORT
Date: | 2008-07-03
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 1:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 4:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-10
A crew from Coastal Concrete placed a total of 73 cy for the wall from line C.5 to A3 including footings A3 and B3. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid range water reducer.
Concrete Testing Services.
Slump: 5" to 6-3/4" Air content: 4.5% Concrete Temperature: 82.5 deg. F. Air Temperature: 75 deg. F One set of four cylinders was cast for compressive strength testing.

## 6-23-08
DAILY FIELD REPORT
Date: | 2008-06-23
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 1:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-25
Picked up two set (#9) of four cylinders each for compressive strength testing.
Cylinder Pickup

## 6-20-08
DAILY FIELD REPORT
Date: | 2008-06-20
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Adam Lyons
Leave: | 10:30 | Mileage: | 96 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 4.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-23
A crew from Coastal Concrete placed a total of 31.5cy for the elevator pit floor including footings "D"-3 and "C"-3, footers "D"-2.4, "C"-2.4,"G"-1.6, "B"-1.6, and wall footings from "B.5"-4 to "A"-2.5. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid range water reducer.
Concrete Testing Services.
Slump: 4 3/4" to 5" Air content: 5.8 to 6.2% Concrete Temp.: 72 to 75 deg. F. Air Temp.: 80 deg. F One set (#9) of four cylinders was cast for compressive strength testing.

## 6-16-08
DAILY FIELD REPORT
Date: | 2008-06-16
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 4:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 5:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-23
Picked up two set (#7 & 8) of four cylinders each for compressive strength testing.
Cylinder Pickup

## 6-13-08
DAILY FIELD REPORT
Date: | 2008-06-13
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Adam Lyons
Leave: | 7:30 | Mileage: | 112 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:15 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 7.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-17
A crew from Coastal Concrete placed a total of 74cy for foundation walls along line 1 "B.5-A", line "A" 1-2, the footings for stairwell "A", and a pier located at "E"-2. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump.
Concrete Testing Services.
Slump: 4 3/4" to 6" Air content: 5.4 to 6.0% Concrete Temp.: 73 to 74 deg. F. Air Temp.: 77.5 to 83 deg. F Two sets (#7 and #8) of four cylinders were cast for compressive strength testing.

## 5-30-08
DAILY FIELD REPORT
Date: | 2008-05-30
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 7:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 8:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-02
Picked up one set (#6) of four cylinders for compressive strength testing.
Cylinder Pickup

## 5-29-08
DAILY FIELD REPORT
Date: | 2008-05-29
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 9:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-02
A crew from Coastal Concrete placed a total of 17cy for footing foundation at the following location: line C1, to line A2 & from G2 to G3. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via truck chute. Also, retrieved two sets (#4 & 5) of cylinders made on 5-27-08
Concrete testing and pick up cylinders
Slump: 5" Air content: 5.9% Concrete Temp.: 68.1deg. F. Air Temp.: 70.8 deg. F One set (#6) of four cylinders was cast for compressive strength testing.

## 5-27-08
DAILY FIELD REPORT
Date: | 2008-05-27
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Portal to Portal |  | Expenses |  | Signed: | Mike Sullivan
Leave: | 9:00 | Mileage: | 4 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-29
A crew from Coastal Concrete placed a total of 87cy for foundation wall at the following location: North side and West side. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi containing Polyweed 997 ( MRWR ). The concrete was placed via pump chute by North East Pumping Services.
Concrete testing
Slump: 5 to 6" After MRWR Air content: 7.5 to 7.6% Concrete Temp.: 69 to 71 deg. F. Air Temp.: 80 deg. F Two sets (#4 & 5) of eight cylinders was cast for compressive strength testing.

## 5-15-08
DAILY FIELD REPORT
Date: | 2008-05-15
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-16
Picked up two sets (#'s 2 & 3) of eight cylinders for compressive strength testing.
Cylinder Pickup

## 5-14-08
DAILY FIELD REPORT
Date: | 2008-05-14
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 6:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-16
A crew from Coastal Concrete placed a total of 100cy for footings and foundation wall at the following location: line 1,C.2 to line G,2 & from F4 to C4. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump chute.
Concrete testing
Slump: 3 3/4", 4", 7", 7", 5" Air content: 5.5%, 5.7% Concrete Temp.: 69.2 deg. F. Air Temp.: 73.5 deg. F Two sets (#2&3) of eight cylinders was cast for compressive strength testing.

## 5-2-08
DAILY FIELD REPORT
Date: | 2008-05-02
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Picked up one set (#1) of four cylinders for compressive strength testing.
Pick up cylinders

## 5-1-08
DAILY FIELD REPORT
Date: | 2008-05-01
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 6:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
A crew from Coastal concrete placed a total of 46.5cy for footings and foundation wall at the location: line 4, F to G ; line G, 1 to 4 ; line 1, C to G, and a areaway footing. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via truck chute.
Concrete testing
Slump: 4 1/2", 3 3/4", 5" Air content: 4% Concrete Temp.: 69.6 deg. F. Air Temp.: 49.8 deg. F One set (#1) of four cylinders was cast for compressive strength testing.