## TOC
SUMMIT GEOENGINEERING SERVICES
434 Cony Road, Augusta, Maine 04330
Tel: (207) 621.8334 Fax: (207) 626.9094
TABLE OF CONTENTS
PROJECT NO: |  | 14063
PROJECT NAME: |  | UNE College of Pharmacy
CLIENT: |  | University of New England
DATE | WORK ACTIVITY/LOCATION
2008-05-14 | Concrete testing footings and foundation
2008-05-15 | Cylinder pickup set #'s 2 and 3
2008-05-27 | Concrete testing North and West side foundation wall
2008-05-29 | Concrete tesing footing foundation and cylinder pickup # 4 and 5
2008-05-30 | Cylinder pickup Set #6
2008-06-13 | Concrete testing foundation walls
2008-06-16 | Cylinder pickup sets 7 and 8
2008-06-20 | Concrete testing elevator pit floor
2008-06-23 | Cylinder pickup set 9
2008-07-03 | Concrete testing for wall
2008-07-07 | Cylinder pickup set 10
2008-07-10 | Concrete testing
2008-07-11 | Cylinder pickup set 11
2008-07-18 | Concrete test, # 12
2008-07-31 | Concrete test and cylinder pickup #12
2008-08-01 | Cylinder pickup #13
2008-08-20 | Concrete testing
2008-08-21 | Cylinder pickup #14
2008-08-22 | Concrete testing services

## Density Results Summary
SUMMIT GEOENGINEERING SERVICES
434 Cony Road, Augusta, Maine 04330
Tel: (207) 621.8334 Fax: (207) 626.9094
SUMMIT GEOENGINEERING FIELD DENSITY RESULTS SUMMARY
PROJECT NO: |  | 14063
PROJECT NAME: |  | UNE College of Pharmacy
CLIENT: |  | University of New England
Test Number | Date | Location: | Lift Elevation | Moisture Content % | In-place Density DD PCF | Maximum Density PCF | Percent Compaction | Required Compaction | Remarks
Remarks:
Proctor Information:

## 8-22-08
DAILY FIELD REPORT
Date: | 2008-08-22
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 10:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 2:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 4 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-25
A crew from Coastal Concrete placed a total of 48.5 cy for the South area way and loading dock footing. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 3 1/2" to 5 1/2" Air content: 4.7% Concrete Temperature: 78deg. F. Air Temperature: 65deg. F One set of four cylinders was cast for compressive strength testing.

## 8-21-08
DAILY FIELD REPORT
Date: | 2008-08-21
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Picked up two sets (#14&15) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinders Pickup
NA

## 8-20-08
DAILY FIELD REPORT
Date: | 2008-08-20
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 6:45 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 1:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.25 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
A crew from Pride Concrete Floor placed a total of47 cy for the attic slab, and a crew from Coastal Concrete placed a total of 10cy for the piers on line 4-A. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump. For the attic slab mix # 2 was used with no air, and mix # 1 for the piers with air.
Concrete Testing Services.
Slump: 5" Slump: 5 1/2" Air content: 2.3% Air content: 5.5% Concrete Temperature: 75.5deg. F. Concrete temp.: 75 Air Temperature: 60deg. F Two sets of four cylinders was cast for compressive strength testing.

## 8-01-08
DAILY FIELD REPORT
Date: | 2008-08-01
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 9:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-01
Picked up two sets (#13) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinder Pickup
NA

## 7-31-08
DAILY FIELD REPORT
Date: | 2008-07-31
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 11:30 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 17:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-08-01
A crew from Coastal Concrete placed a total of 52.5 cy for the South area footing, the North area way wall, North masonry pier, pier G 3.6, and entry foundation wall on the East side. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with Polyheed 997 (mid-range water reducer) added at the batch plant. The concrete was placed via pump. Also, picked up cylinder set # 12 cast on 7-18-08
Concrete Testing Services.
Slump: 4" to 5-1/2" Air content: 5.8% Concrete Temperature: 85deg. F. Air Temperature: 80deg. F One set of four cylinders was cast for compressive strength testing.

## 7-18-08
DAILY FIELD REPORT
Date: | 2008-07-18
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Frank Clark
Leave: | 11:15am | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 2:00pm | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.75 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
A crew from Coastal Concrete placed a total of 12.5 cy for the wall on line A from 1 to 2 and the 1' wall around the stairway in the basement.. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi., with a MRWR ( Glenium ) added at the batch plant. The concrete was placed via pump.
Concrete Testing Services.
Slump: 3 3/4" to 5-3/4" Air content: 4.5 to 4.8% Concrete Temperature: 85 to 87 deg. F. Air Temperature: 98 deg. F One set of four cylinders was cast for compressive strength testing.

## 7-11-08
DAILY FIELD REPORT
Date: | 2008-07-11
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 7:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 8:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
Picked up two sets (#11) of four cylinders each for compressive strength testing and controlled storage.
None
Cylinder Pickup
NA

## 7-10-08
DAILY FIELD REPORT
Date: | 2008-07-10
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 1:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-14
A crew from Coastal Concrete placed a total of 8 cy for footing B2.4, stair A wall, and stair B footing. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid-range water reducer.
Concrete Testing Services.
Slump: 5 1/2" Air content: 5.5% Concrete Temperature: 85 deg. F. Air Temperature: 80 deg. F One set of four cylinders was cast for compressive strength testing.

## 7-7-08
DAILY FIELD REPORT
Date: | 2008-07-07
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 10:00 | Mileage: | 4 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 11:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-10
Picked up two set (#10) of four cylinders each for compressive strength testing.
None
Cylinder Pickup
NA

## 7-3-08
DAILY FIELD REPORT
Date: | 2008-07-03
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts: | Gary Kibler - Allied Cook
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 1:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 4:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-07-10
A crew from Coastal Concrete placed a total of 73 cy for the wall from line C.5 to A3 including footings A3 and B3. Concrete was supplied by Dragon Products with a mix design of 3/4" aggregate and a design strength of 3000 psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid range water reducer.
Concrete Testing Services.
Slump: 5" to 6-3/4" Air content: 4.5% Concrete Temperature: 82.5 deg. F. Air Temperature: 75 deg. F One set of four cylinders was cast for compressive strength testing.

## 6-23-08
DAILY FIELD REPORT
Date: | 2008-06-23
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 1:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-25
Picked up two set (#9) of four cylinders each for compressive strength testing.
Cylinder Pickup

## 6-20-08
DAILY FIELD REPORT
Date: | 2008-06-20
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Adam Lyons
Leave: | 10:30 | Mileage: | 96 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 4.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-23
A crew from Coastal Concrete placed a total of 31.5cy for the elevator pit floor including footings "D"-3 and "C"-3, footers "D"-2.4, "C"-2.4,"G"-1.6, "B"-1.6, and wall footings from "B.5"-4 to "A"-2.5. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump.
The concrete contained polyhead 997, a mid range water reducer.
Concrete Testing Services.
Slump: 4 3/4" to 5" Air content: 5.8 to 6.2% Concrete Temp.: 72 to 75 deg. F. Air Temp.: 80 deg. F One set (#9) of four cylinders was cast for compressive strength testing.

## 6-16-08
DAILY FIELD REPORT
Date: | 2008-06-16
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 4:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 5:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-23
Picked up two set (#7 & 8) of four cylinders each for compressive strength testing.
Cylinder Pickup

## 6-13-08
DAILY FIELD REPORT
Date: | 2008-06-13
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Adam Lyons
Leave: | 7:30 | Mileage: | 112 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 3:15 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 7.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-17
A crew from Coastal Concrete placed a total of 74cy for foundation walls along line 1 "B.5-A", line "A" 1-2, the footings for stairwell "A", and a pier located at "E"-2. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump.
Concrete Testing Services.
Slump: 4 3/4" to 6" Air content: 5.4 to 6.0% Concrete Temp.: 73 to 74 deg. F. Air Temp.: 77.5 to 83 deg. F Two sets (#7 and #8) of four cylinders were cast for compressive strength testing.

## 5-30-08
DAILY FIELD REPORT
Date: | 2008-05-30
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 7:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 8:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 1 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-02
Picked up one set (#6) of four cylinders for compressive strength testing.
Cylinder Pickup

## 5-29-08
DAILY FIELD REPORT
Date: | 2008-05-29
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 9:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-06-02
A crew from Coastal Concrete placed a total of 17cy for footing foundation at the following location: line C1, to line A2 & from G2 to G3. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via truck chute. Also, retrieved two sets (#4 & 5) of cylinders made on 5-27-08
Concrete testing and pick up cylinders
Slump: 5" Air content: 5.9% Concrete Temp.: 68.1deg. F. Air Temp.: 70.8 deg. F One set (#6) of four cylinders was cast for compressive strength testing.

## 5-27-08
DAILY FIELD REPORT
Date: | 2008-05-27
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Portal to Portal |  | Expenses |  | Signed: | Mike Sullivan
Leave: | 9:00 | Mileage: | 4 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 12:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 3.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-29
A crew from Coastal Concrete placed a total of 87cy for foundation wall at the following location: North side and West side. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi containing Polyweed 997 ( MRWR ). The concrete was placed via pump chute by North East Pumping Services.
Concrete testing
Slump: 5 to 6" After MRWR Air content: 7.5 to 7.6% Concrete Temp.: 69 to 71 deg. F. Air Temp.: 80 deg. F Two sets (#4 & 5) of eight cylinders was cast for compressive strength testing.

## 5-15-08
DAILY FIELD REPORT
Date: | 2008-05-15
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-16
Picked up two sets (#'s 2 & 3) of eight cylinders for compressive strength testing.
Cylinder Pickup

## 5-14-08
DAILY FIELD REPORT
Date: | 2008-05-14
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 6:30 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6.5 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
|  |  |  | Sent: | 2008-05-16
A crew from Coastal Concrete placed a total of 100cy for footings and foundation wall at the following location: line 1,C.2 to line G,2 & from F4 to C4. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via pump chute.
Concrete testing
Slump: 3 3/4", 4", 7", 7", 5" Air content: 5.5%, 5.7% Concrete Temp.: 69.2 deg. F. Air Temp.: 73.5 deg. F Two sets (#2&3) of eight cylinders was cast for compressive strength testing.

## 5-2-08
DAILY FIELD REPORT
Date: | 2008-05-02
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 8:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 10:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 2 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
Picked up one set (#1) of four cylinders for compressive strength testing.
Pick up cylinders

## 5-1-08
DAILY FIELD REPORT
Date: | 2008-05-01
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses |  | Signed: | Abdoul Boubacar
Leave: | 12:00 | Mileage: | 5 | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: | 6:00 | Density Gauge: |  |  | Tom Melican, John B. Sullivan Corp.
TOTAL: | 6 | Other:
|  |  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent:
A crew from Coastal concrete placed a total of 46.5cy for footings and foundation wall at the location: line 4, F to G ; line G, 1 to 4 ; line 1, C to G, and a areaway footing. Concrete was supplied by Dragon with a mix design of 3/4" aggregate and a design strength of 3000psi. The concrete was placed via truck chute.
Concrete testing
Slump: 4 1/2", 3 3/4", 5" Air content: 4% Concrete Temp.: 69.6 deg. F. Air Temp.: 49.8 deg. F One set (#1) of four cylinders was cast for compressive strength testing.

## Template
DAILY FIELD REPORT
Date:
Project: | UNE Pharmacy Building
Project #: | 14063
Site Contacts:
Purpose of Visit:
Work Activities:
.
Test Results:
Remarks:
Portal to Portal |  | Expenses | Signed:
Leave: |  | Mileage: | cc: | Scott Sullivan, John B. Sullivan Corp.
Return: |  | Density Gauge: |  | Tom Melican, John B. Sullivan Corp.
TOTAL: |  | Other:
|  |  | Reviewed: | Darrell A. Gilman, CMT Manager
Sent: