Spaulding Engineering and Construction Services, Inc.

24 Common Street ~ Waterville, Maine  04901

Phone (207) 861-9923 ~ Fax (207) 861-9923

# WEEKLY CONSTRUCTION REPORT

## Report # 2

| Project: | CMP Portland Service Center – 5’-6” East Truck Bay Addition |  | Date: 10-03-11 |
| --- | --- | --- | --- |
| Location: | Portland, Maine |  |  |  |
| Contractor | H.E. Callahan Construction Company |  |  |  |
| Client: | Central Maine Power Company |  |  |  |
| From: | Jack Belyeu | SECS-Technician |
| To: | Bob Meader |  |

| Work Completed This Week: | (W/E) 10-01-11 |
| --- | --- |

DAYS ON SITE: (6)

Completed all reinforcing and formwork for the placement of the concrete walls and piers.

Placed 18 cubic yards of concrete for new walls and piers on Tuesday, September 27.

Stripped footing, wall and pier forms.

Placed compacted gravel backfill inside and outside.

Installed wall inside insulation.

Completed remaining demolition of the existing concrete slab to allow tie-in of the new concrete slab on Saturday 10-01-11.

| 6 | Days worked this week | 0 | Day(s) lost due to inclement weather. |
| --- | --- | --- | --- |

Manpower

| H.E. Callahan Construction |  | Varied 1-2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Colex |  | Varied |  |  |  |  |
| Williams Concrete |  | Varied |  |  |  |  |
| S.W. Cole |  | 1 |  |  |  |  |

Project Status

| 15% |  | Complete |  | Scheduled Completion Date | 11/30/11 |
| --- | --- | --- | --- | --- | --- |

| X |  | on schedule | or | _______ days/weeks ahead/behind schedule |
| --- | --- | --- | --- | --- |

Work Planned for Next Week:

Install vapor barrier.

Install reinforcing and forms for concrete slab placement.

Place concrete slab on Wednesday, October 5.

Start cutting existing siding as required.

Structural steel to arrive onsite on Friday, October 7.

Problems/Issues:

Visitors:

Dan Spaulding, SECS – Tuesday 9-27

Nick Adams, City of Portland – Tuesday 9-27

Other:

Signature _____________________

Jack Belyeu

CC: Marc Geaumont, CMP

Steve Willette, CMP

Tom Daniels, CMP

Dave Lepage, HEC

Phil DiPierro, City of Portland

Jonathan Blanchard, HEC

Attachments: Photos

09-27-11 Wall and pier forming and reinforcing for new addition walls and piers.

09-27-11 Bracing of pier forms.

09-27-11 Formwork and recess in wall to accept new slab.

09-27-11 Placing concrete at new addition south wall.

09-27-11 Placing concrete at new addition north wall.

09-27-11 Concrete in place.