Copyright 2002, The American Institute of Architects (AIA)

SECTION 012900 - PAYMENT PROCEDURES

This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

- GENERAL

      - RELATED DOCUMENTS

        - Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

      - SUMMARY

        - This Section specifies administrative and procedural requirements necessary to prepare and process Applications for Payment.

      - DEFINITIONS

Delete this Article if AIA Document A201 or EJCDC Document 1910-8 is used for Project.  Retain only if the Schedule of Values is not mentioned in the Conditions of the Contract.

        - Schedule of Values:  A statement furnished by Contractor allocating portions of the Contract Sum to various portions of the Work and used as the basis for reviewing Contractor's Applications for Payment.

      - SCHEDULE OF VALUES

        - Coordination:  Coordinate preparation of the Schedule of Values with preparation of Contractor's Construction Schedule.

          - Correlate line items in the Schedule of Values with other required administrative forms and schedules, including the following:

Revise list below to suit Project.

            - Application for Payment forms with Continuation Sheets.

            - Submittals Schedule.

            - Contractor's Construction Schedule.

Revise seven-day time period in subparagraph below to suit Project.

          - Submit the Schedule of Values to Contracting Officer at earliest possible date but no later than seven days before the date scheduled for submittal of initial Applications for Payment.

Delete subparagraph below if phasing is not required.  See Evaluations in Division 1 Section "Summary."  For large projects, consider revising below to provide subschedules for separate floors or large individual areas.

          - Subschedules:  Where the Work is separated into phases requiring separately phased payments, provide subschedules showing values correlated with each phase of payment.

Retain paragraph and subparagraphs below.  Revise to suit Project.  If desired, include a sample schedule of values at end of Section.

        - Format and Content:  Use the Project Manual table of contents as a guide to establish line items for the Schedule of Values.  Provide at least one line item for each Specification Section.

          - Identification:  Include the following Project identification on the Schedule of Values:

Revise list below to suit Project.

            - Project name and location.

            - Name of Architect.

            - Government’s Project Number

            - Contractor's name and address.

            - Date of submittal.

          - Submit draft of AIA Document G703 or Contractor’s approved equivalent Continuation Sheets.

Retain subparagraph above or first subparagraph and associated subparagraphs below.

          - Arrange the Schedule of Values in tabular form with separate columns to indicate the following for each item listed:

Revise list below to suit Project.

            - Related Specification Section or Division.

            - Description of the Work.

            - Name of subcontractor.

            - Name of manufacturer or fabricator.

            - Name of supplier.

            - Change Orders (numbers) that affect value.

            - Dollar value.

              - Percentage of the Contract Sum to nearest one-hundredth percent, adjusted to total 100 percent.

          - Provide a breakdown of the Contract Sum in enough detail to facilitate continued evaluation of Applications for Payment and progress reports.  Coordinate with the Project Manual table of contents.  Provide several line items for principal subcontract amounts, where appropriate.  Include separate line items under required principal subcontracts for operation and maintenance manuals, punch list activities, Project Record Documents, and demonstration and training in the amount of 5 percent of the Contract Sum.

          - Round amounts to nearest whole dollar; total shall equal the Contract Sum.

Retain first subparagraph and associated subparagraph below.  Strengthen provisions below to protect against undue front-end loading if required.

          - Provide a separate line item in the Schedule of Values for each part of the Work where Applications for Payment may include materials or equipment purchased or fabricated and stored, but not yet installed.

            - Differentiate between items stored on-site and items stored off-site.  If specified, include evidence of insurance or bonded warehousing.

          - Provide separate line items in the Schedule of Values for initial cost of materials, for each subsequent stage of completion, and for total installed value of that part of the Work.

Delete subparagraph below if Specifications do not include unit-cost allowances.  Do not confuse unit-cost allowances with unit prices.  See Evaluations in Division 1 Section "Allowances" for discussion on unit-cost allowances, including potential differences that can occur in dollar amounts between bidders as a result of different procedures in estimating quantities.

Retain subparagraph and associated subparagraph below.  Revise to suit Project.  Owner's financial advisors usually insist on this requirement.  See Evaluations for discussion on overhead distribution.

          - Each item in the Schedule of Values and Applications for Payment shall be complete.  Include total cost and proportionate share of general overhead and profit for each item.

            - Temporary facilities and other major cost items that are not direct cost of actual work-in-place may be shown either as separate line items in the Schedule of Values or distributed as general overhead expense, at Contractor's option.

Revise subparagraph below to suit Project.  As an alternate approach to method described, include each Change Order as a new line item or a separate sheet.

          - Schedule Updating:  Update and resubmit the Schedule of Values before the next Applications for Payment when Change Orders or Construction Change Directives result in a change in the Contract Sum.

      - APPLICATIONS FOR PAYMENT

See Evaluations for discussion on waiver of liens and other documentation involved.

        - Each Application for Payment shall be consistent with previous applications and payments as certified by Contracting Officer and paid for by Owner.

          - Initial Application for Payment, Application for Payment at time of Substantial Completion, and final Application for Payment involve additional requirements.

Retain first two paragraphs and subparagraphs below when the Owner/Contractor Agreement stipulates payment dates.  These dates might affect Contractor's need to have sufficient funds available to finance construction operations.  Review dates in a preconstruction conference if a potential problem arises.

        - Payment Application Times:  The date for each progress payment is indicated in the Agreement between Owner and Contractor.  The period of construction Work covered by each Application for Payment is the period indicated in the Agreement.

If the Agreement does not state payment dates, delete paragraph above and retain paragraph below.  Change dates to suit Project.

Retain paragraph below if an industry standard form is used.  Revise if Owner uses another form.  AIA forms described below are available at most AIA Chapter offices.  EJCDC Document 1910-8-E is another standard-industry form owners often use.  Alternate forms may include local construction-industry forms or lending institution's own standard forms.

        - Payment Application Forms:  Use AIA Document G702 and AIA Document G703 or Contractor’s approved equivalent Continuation Sheets as form for Applications for Payment.

Delete paragraph above and retain first paragraph below if a standard-industry form is not used.

        - Application Preparation:  Complete every entry on form.  Notarize and execute by a person authorized to sign legal documents on behalf of Contractor.  Contracting Officer will return incomplete applications without action.

          - Entries shall match data on the Schedule of Values and Contractor's Construction Schedule.  Use updated schedules if revisions were made.

          - Include amounts of Change Orders and Construction Change Directives issued before last day of construction period covered by application.

Revise number of copies in paragraph below to suit Owner's Project requirements.

        - Transmittal:  Submit 3 signed and notarized original copies of each Application for Payment to Contracting Officer by a method ensuring receipt within 24 hours.  One copy shall include waivers of lien and similar attachments if required.

          - Transmit each copy with a transmittal form listing attachments and recording appropriate information about application.

Insert instructions for preparation and submittal of waivers or releases here if not stated in the Supplementary Conditions.

Lien laws vary widely in the U.S.  Owner's legal counsel and financial advisors, not Architect, should establish requirements for waivers of mechanic's lien.  First two alternative paragraphs and associated subparagraphs below are examples of ways to handle waivers of lien.  Select one or replace both with another effective method.

        - Waivers of Mechanic's Lien:  With each Application for Payment, submit waivers of mechanic's lien from every entity who is lawfully entitled to file a mechanic's lien arising out of the Contract and related to the Work covered by the payment.

          - Submit partial waivers on each item for amount requested in previous application, after deduction for retainage, on each item.

          - When an application shows completion of an item, submit final or full waivers.

          - Owner reserves the right to designate which entities involved in the Work must submit waivers.

Delete subparagraph below and insert a specific form or special requirements where predetermined.  See Evaluations.

          - Waiver Forms:  Submit waivers of lien on forms, executed in a manner acceptable to Owner.

        - Initial Application for Payment:  Administrative actions and submittals that must precede or coincide with submittal of first Application for Payment include the following:

Revise list below to suit Project.

          - List of subcontractors.

          - Schedule of Values.

          - Contractor's Construction Schedule (preliminary if not final).

          - Products list.

          - Schedule of unit prices.

          - Submittals Schedule (preliminary if not final).

          - List of Contractor's staff assignments.

          - List of Contractor's principal consultants.

          - Copies of building permits.

          - Copies of authorizations and licenses from authorities having jurisdiction for performance of the Work.

          - Initial progress report.

          - Report of preconstruction conference.

          - Certificates of insurance and insurance policies.

Delete items from those listed below submitted before executing the Contract.

          - Performance and payment bonds.

          - Data needed to acquire Owner's insurance.

          - Initial settlement survey and damage report if required.

        - Application for Payment at Substantial Completion:  After issuing the Certificate of Substantial Completion, submit an Application for Payment showing 100 percent completion for portion of the Work claimed as substantially complete.

          - Include documentation supporting claim that the Work is substantially complete and a statement showing an accounting of changes to the Contract Sum.

          - This application shall reflect Certificates of Partial Substantial Completion issued previously for Owner occupancy of designated portions of the Work.

        - Final Payment Application:  Submit final Application for Payment with releases and supporting documentation not previously submitted and accepted, including, but not limited, to the following:

Revise list below to suit Project.  Consult Owner about the need for additional affidavits and other requirements.

          - Evidence of completion of Project closeout requirements.

          - Insurance certificates for products and completed operations where required and proof that taxes, fees, and similar obligations were paid.

          - Updated final statement, accounting for final changes to the Contract Sum.

          - AIA Document G706, "Contractor's Affidavit of Payment of Debts and Claims" or Contractor’s approved equivalent.

          - AIA Document G706A, "Contractor's Affidavit of Release of Liens" or Contractor’s approved equivalent.

Delete first subparagraph below if a surety is not involved.

          - AIA Document G707, "Consent of Surety to Final Payment" or Contractor’s approved equivalent.

          - Evidence that claims have been settled.

          - Final meter readings for utilities, a measured record of stored fuel, and similar data as of date of Substantial Completion or when Owner took possession of and assumed responsibility for corresponding elements of the Work.

          - Final, liquidated damages settlement statement.

- PRODUCTS (Not Used)

- EXECUTION (Not Used)

If Owner requires use of sample forms, include a sample copy here.

END OF SECTION 012900