SECTION 013200 – CONSTRUCTION PROGRESS DOCUMENTATION

PART 1 - GENERAL

1.1	COORDINATION

- Coordinate both the timing and the listing of reports and other activities required by provisions of this and other sections, to provide consistency and logical coordination between submitted reports or lists.  Maintain coordination and correlation between separate reports by updating at monthly or shorter time intervals.  Make appropriate distribution of each report and updated report to entities involved in the work.

- Documentation of Existing: Provide videotape documentation of all existing to remain elements, including, but not limited to: windows, doors, wall paneling, judges’ benches, witness boxes, bookcases, and cabinets, and submit for record prior to beginning work.

1.2	CONSTRUCTION PROGRESS SCHEDULE

A.	Refer to Construction Contract Clause "Schedules for Construction Contracts."

B.	Individual Work Stages:  Show significant stages for each category or unit of work, including (where applicable), but not necessarily limited to, subcontract lettering, submittals, purchases, mockups, fabrication, sample testing, deliveries, installation, testing, adjusting, curing, start-up and placement into final use and operation.

C.	Distribution:  Following the initial submittal to and response by the Contracting Officer, print and distribute progress schedule to the Contracting Officer (3 copies), separate Contractors (if any), principal subcontractors and suppliers or fabricators, and others with a need-to-know schedule-compliance requirement. When revisions are made, distribute updated issues to same entities, and post in same locations.  Delete entities from distribution when they have completed their assigned work and are no longer involved in performance of scheduled work.

1.3	SCHEDULE SUBMISSIONS

A.	General:  Submit construction progress schedule within  7  calendar days after the Notice to Proceed is received.  The construction progress schedule shall include all work related submittals.

B.	Form:  Prepare the schedule in chronological order of submittals.  Show category of the submittal, name of subcontractor, a generic description of work covered, related section numbers, the activity or event number on the progress schedule, the scheduled date for first submittal, resubmittal, and the final release or approval by the Contracting Officer.

- Schedule Updating:  Revise the schedule weekly, and each time revisions have been recognized or made.  Resubmit for the Owner’s review and comment.

  - CONTRACTOR'S CONSTRUCTION SCHEDULE (CPM SCHEDULE)

CPM schedules are more complex than Gantt-chart schedules.  Delete this article if not required.  See Evaluations.

        - General:  Prepare network diagrams using AON (activity-on-node) format such as provided by  Microsoft “Project” or similar scheduling program.

Projects using CPM schedules should begin with a start-up network diagram of type described in first paragraph below or a start-up bar-chart schedule as described in "Start-Up Construction Schedule" Article above.

        - Start-up Network Diagram:  Submit diagram within 14 days of date established for the Notice to Proceed.  Outline significant construction activities for the first 90 days of construction.  Include skeleton diagram for the remainder of the Work.

Revise first paragraph below to suit Project.

        - CPM Schedule:  Prepare Contractor's construction schedule using a time-scaled CPM network analysis diagram for the Work.

          - Project requires access and work within the Jetport terminal gate areas which are subject to significant security restrictions. Indicate on the CMP schedule specific dates and times identifying this work. See Section 013000 for notification requirements in addition to this schedule requirement.

          - Develop network diagram in sufficient time to submit CPM schedule so it can be accepted for use no later than 60 days after date established for the Notice to Proceed.

            - Failure to include any work item required for performance of this Contract shall not excuse Contractor from completing all work within applicable completion dates, regardless of Architect's approval of the schedule.

          - Conduct educational workshops to train and inform key Project personnel, including subcontractors' personnel, in proper methods of providing data and using CPM schedule information.

          - Establish procedures for monitoring and updating CPM schedule and for reporting progress.  Coordinate procedures with progress meeting dates.

Subparagraph below coordinates between working days of time and calendar days.  Under AIA Document A201, Contract Time is in calendar days.

          - Use "one workday" as the unit of time for individual activities.  Indicate nonworking days and holidays incorporated into the schedule in order to correlate with Contract Time.

Revise first paragraph below to suit Project.

        - CPM Schedule Preparation:  Prepare a list of all activities required to complete the Work.  Using the start-up network diagram, prepare a skeleton network to identify probable critical paths.

          - Activities:  Indicate the estimated time duration, sequence requirements, and relationship of each activity in relation to other activities.  Include estimated time frames for the following activities:

Revise list below to suit Project.

            - Preparation and processing of submittals.

            - Mobilization and demobilization.

            - Purchase of materials.

            - Delivery.

            - Fabrication.

            - Utility interruptions.

            - Installation.

            - Work by Owner that may affect or be affected by Contractor's activities including relocation of furnishings.

            - Punch list and final completion.

            - Activities occurring following final completion.

          - Critical Path Activities:  Identify critical path activities, including those for interim completion dates.  Scheduled start and completion dates shall be consistent with Contract milestone dates.

          - Processing:  Process data to produce output data on a computer-drawn, time-scaled network.  Revise data, reorganize activity sequences, and reproduce as often as necessary to produce the CPM schedule within the limitations of the Contract Time.

          - Format:  Mark the critical path.  Locate the critical path near center of network; locate paths with most float near the edges.

            - Subnetworks on separate sheets are permissible for activities clearly off the critical path.

        - Contract Modifications:  For each proposed contract modification and concurrent with its submission, prepare a time-impact analysis using a network fragment to demonstrate the effect of the proposed change on the overall project schedule.

        - Initial Issue of Schedule:  Prepare initial network diagram from a sorted activity list indicating straight "early start-total float."  Identify critical activities.  Prepare tabulated reports showing the following:

          - Contractor or subcontractor and the Work or activity.

          - Description of activity.

          - Principal events of activity.

          - Immediate preceding and succeeding activities.

          - Early and late start dates.

          - Early and late finish dates.

          - Activity duration in workdays.

          - Total float or slack time.

          - Average size of workforce.

        - Schedule Updating:  Update schedule at a minimum on a weekly basis.  Concurrent with making revisions to schedule, prepare tabulated reports showing the following:

          - Identification of activities that have changed.

          - Changes in early and late start dates.

          - Changes in early and late finish dates.

          - Changes in activity durations in workdays.

          - Changes in the critical path.

          - Changes in total float or slack time.

          - Changes in the Contract Time.

1.5			REPORTS

A.	Daily Construction Reports:  Prepare a daily construction report, recording the following information concerning events at the site; and submit duplicate copies to the Government Representative at weekly intervals:

1.	List of subcontractors at the site.

2.	List of separate contractors at the site.

3.	Approximate count of personnel at the site.

4.	High and low temperatures, general weather conditions.

5.	Accidents (refer to accident reports).

6.	Meetings and significant decisions.

7.	Unusual events (refer to special reports).

8.	Stoppages, delays, shortages, losses.

9.	Meter readings and similar recordings.

10.	Emergency procedures.

11.	Orders and requests of governing authorities.

12.	Change Orders received, implemented.

13.	Services connected, disconnected.

14.	Equipment or system tests and start-ups.

15.	Partial Completions, occupancies.

16.	Substantial Completions authorized.

B.	Field Correction Report:  When the need to take corrective action that requires a departure from the Contract Documents arises, prepare a detailed report including a statement describing the problem and recommended changes.  Indicate reasons the Contract Documents cannot be followed.  Submit a copy to the Government Representative t immediately.

1.6	SPECIAL REPORTS

A.	General:  Submit special reports directly to the Government within one day of an occurrence.  Submit a copy to the Government Representative and other parties affected by the occurrence.

B.	Reporting Unusual Events:  When an event of an unusual and significant nature occurs at the site, prepare and submit a special report.  List the chain of events, persons participating, response by the Contractor's personnel, an evaluation of the results or effects and similar pertinent information.  Advise the Government Representative in advance when such events are known or predictable.

PART 2 - PRODUCTS (Not Applicable)

PART 3 - EXECUTION (Not Applicable)

END OF SECTION 01310