SECTION 017700 – CLOSEOUT PROCEDURES

PART 1 - GENERAL

1.1	SUMMARY

A.	General:  This section includes general requirements near end of Contract Time, in preparation for final acceptance, final payment, normal termination of contract, occupancy and similar actions evidencing completion of the work.  Specific requirements for individual units of work are specified in sections of Division 02 through 33.  Time of closeout is directly related to "Substantial Completion", and therefore may be either a single time period for entire work or a series of time periods for individual parts of the work which have been noted as substantially complete at different dates.

1.2	PREREQUISITES TO SUBSTANTIAL COMPLETION

A.	General:  Prior to requesting inspection for certification of substantial completion (for either entire work or portions thereof), complete the following and list known exceptions in request:

1.	In progress payment request, coincident with or first following date claimed, show either 100% completion for portion of work claimed as "substantially complete", or list incomplete items, value of incompletion, and reasons for being incomplete.  Include supporting documentation for completion as indicated in these contract documents.

B.	Inspection Procedures:  Upon receipt of Contractor's request, the Contracting Officer will either proceed with inspection or advise Contractor of prerequisites not fulfilled.  Following initial inspection, the Contracting Officer will note substantial completion, or advise Contractor of work which must be performed and repeat inspection when requested and assured that work has been substantially completed.  Results of completed inspection will form initial "punch-list" for final acceptance.

1.3	PREREQUISITES TO FINAL ACCEPTANCE

A.	General:  Prior to requesting final inspection for certification of final acceptance and final payment, as required by  Contract Clauses, complete the following and list known exceptions (if any) in request:

1.	Submit final payment request with final releases and supporting documentation not previously submitted and accepted.

2.	Submit copy of final punch-list of itemized work to be completed or corrected, stating that each item has been completed or otherwise resolved for acceptance.

3.	Submit specific warranties, workmanship/maintenance bonds, maintenance agreements, final certifications and similar documents.

4.	Submit record as built drawings, final project photographs, property survey, and similar final record information.

5.	Deliver tools, spare parts, extra stocks of materials, and similar physical items to Government.

6.	Make final change-over of locks and transmit keys to the Government Representative and advise Government personnel of change-over in security provisions.

7.	Complete final cleaning up requirements, including touch-up painting of marred surfaces.

8.	Touch-up and otherwise repair and restore marred exposed finishes.

B.	Re-inspection Procedure:  Upon receipt of Contractor's notice that the work has been completed, including punch-list items resulting from earlier inspections, and excepting incomplete items delayed because of acceptable circumstances, the Government Representative will re-inspect the work.    If necessary, procedure will be repeated.

- Upon completion of re-inspection of the final spaces to be turned over the Government, the Government Representative will either prepare certificate of final acceptance or advise Contractor of work not completed or obligations not fulfilled as required for final acceptance.

1.4	RECORD DOCUMENT SUBMITTALS

A.	General:  As work progresses, prepare and maintain record documents as specified herein.  Each record shall be certified by the Contractor and the Government Representative.  Do not use record documents for construction purposes; protect from deterioration and loss in a secure, fire-resistive location accessible to the Contracting Officer for reference during normal working hours.  Upon completion, turn record documents over to the Contracting Officer as specified in the “Document Security Notice”.  Follow all procedures contained therein for document disposal.

B.	Record Drawings:  Maintain a white-print set (blue-line or black-line) of contract drawings (including amendment and change order drawings) and shop drawings in clean, undamaged condition, with mark-up of actual installations which vary from the work as originally shown.  
1.	Mark whichever drawing is most capable of showing "field" condition fully and accurately; r, 
2.	Where shop drawings are used for mark-up, record a cross-reference at corresponding location on working drawings.  
3.	Mark with red erasable pencil and, where feasible, use other colors to distinguish between variations in separate categories of work.  
4.	Mark-up new information which is recognized to be of importance, but was for some reason not shown on either contract drawings or shop drawings.  Give particular attention to concealed work, which would be difficult to measure and record at a later date.  
5.	Note related change order numbers where applicable.  
6.	Organize record drawing sheets into manageable sets, bind with durable paper cover sheets, and print suitable titles, dates and other identification on cover of each set.

C.	Record Specifications:  Maintain one copy of complete specifications, including amendments, change orders and similar modifications issued in printed form during construction, and mark-up variations in actual work in comparison with text of specifications and modifications as issued.  Give particular attention to substitutions, selection of options, and similar information on work where it is concealed or cannot otherwise be readily discerned at a later date by direct observation.  Note related record drawing information and product data, where applicable.

D.	Progress and Final Photographs:  For each building or structure under contract, provide the following:

- All photography for the project shall be performed with a digital camera. GSA shall receive electronic copies of all photos within 5 days of the time they are taken. At the completion of the project, a CD of all photos shall be delivered to GSA.

- At the completion of the project, photos shall be taken to illustrate the entire area of work as well as adjacent areas/materials.

- At least 1 shot daily of each scope of work item shall be produced with such artistic skill as to be suitable, in the Contracting Officer's opinion, for exhibition and reproduction.

- If progress photographs are not furnished within five days of the date when due or within five days after demand, the Contracting Officer will cause such photographs to be taken and the cost will be charged to the Contractor.  Furnish photographs as soon as possible under the specified light conditions.

E.	Miscellaneous Record Submittals:  Refer to other sections of these specifications for requirements of miscellaneous record-keeping and submittals in connection with actual performance of the work.  Immediately prior to date(s) of substantial completion, complete miscellaneous records and place in good order, properly identified and bound or filed, ready for continued use and reference.  Turn over to the Contracting Officer prior to final acceptance.

PART 2 - PRODUCTS (Not Applicable)

PART 3 - EXECUTION

3.1	FINAL CLEANING

A.	Comply with manufacturer's instructions for cleaning operation.  The following is required in addition to special cleaning specified in technical sections.

1.	Remove labels which are not required as permanent labels.

2.	Clean transparent materials, including mirrors and window/door glass, to a polished condition, removing substances which are noticeable as vision obscuring materials.  Replace broken glass and damaged transparent materials.

3.	Wipe surfaces of equipment clean.  Remove excess lubrication and other substances.

4.	Remove debris and surface dust from limited-access spaces.

5.	Clean light fixtures and lamps so as to function with full efficiency.

- Clean project site of litter and foreign substances.  Sweep paved areas to a broom-clean condition; remove stains, petrochemical spills and other foreign deposits. Rake grounds which are neither planted nor paved, to a smooth, even-textured surface.

- And all other ITEMS/AREAS as directed by the Government Representative

B.	Removal of Protection:  Except as otherwise indicated or requested by the Contracting Officer, remove temporary protection devices and facilities which were installed during course of the work to protect previously completed work during remainder of construction period.

C.	Completion of contract:  The Contractor shall notify the Contracting Officer, in writing, when all work and services required under this contract are complete.

END OF SECTION 017700