# MEMORANDUM

- TO:	Barbara Barhydt

- FROM:	Lauren Swett

- DATE:	February 9, 2007

- RE:	1039 Riverside Street, Second Tee Condominium Business Park – Inspection for Reduction in Performance Guarantee

This memo documents the results of an inspection of the Second Tee Condominium Business Park site located at 1039 Riverside Street in Portland.  On February 6, 2007, a site visit and meeting with the owner, Bob Gaudreau, was conducted by Lauren Swett from Woodard & Curran.  A site plan dated July 2005 was used for the inspection.

The following items were observed at the site:

- The road through the site has been completed.  Sidewalks, parking lots, loading areas and entrances around the future locations of buildings 1, 2, 10, 11, and 14 have not yet been completed.

- Granite curbing installed within the site could not be seen because of snow and ice.

- Completed earthwork was not observed.  Based on the grading plan, most of the grade changes will be made around building 14 which has not been constructed yet.

- From the conversation with Bob Gaudreau, all underground utilities, including sewer, water, and stormwater, have been installed.  Connections to future buildings 1, 2, 10, 11, and 14 remain to be installed following the buildings’ construction.  In addition, the site’s four water quality units have been installed.

- A lighting plan was not included with the site plan provided for inspection.  14 installed lights were observed throughout the whole site.

- None of the erosion control measures were observed at the site.  Any erosion control measures in place were covered with snow, and a majority of the silt fence specified on the plans is located around the buildings that have not yet been constructed.

- White Pine and Crabapple trees were observed throughout the site.  The number of trees shown on the plans and given in the performance guarantee cost estimate are not the same.  There is also a discrepancy in the total cost of white pines.  In the cost estimate, $15,625 was allotted for 29 trees at $125 each.

In 2005, the original site was reduced by an amount of $368,889.78.  Following this reduction, an additional area was added to the site.  The recommended amount for a second reduction, including both the original and added site, is $375,927.87.  This reduction is for only the private portion of the project.  A spreadsheet showing the breakdown of expenses for the reduction is included.

If you have any questions about the information listed above, please don’t hesitate to contact me.

LJS

203939

Attachments: Cost Estimate Spreadsheet